## Worksheet
# | PIC | Produk | Project Type | Mitra | Nama Projek | Status | Progress SIT (%) | Progress UAT (%) | Tanggal Assign
1 | AAP | ATM Bersama | Sertifikasi | Bank BNI | [Regressi] Implementasi Perbaikan Bit 100 BNI as Destination untuk Transaksi dari Interkoneksi Domestik | Project Done |  |  | 2021-01-28
2 | RAS | ATM Bersama Debit | Sertifikasi | Bank NTT | Implementasi Layanan ATMB Debit sebagai Acquirer di Bank NTT | Monitoring | 100 | 100 | 2021-01-28
3 | HSO | ATM Bersama Debit | Internal Test | Bank MANTAP | [Regressi] Implementasi Layanan ATMB Debit as Issuer di Bank Mantap | Project Done |  |  | 2021-01-28
4 | HSO | ATM Bersama | Sertifikasi | Bank Mayapada | Implementasi Layanan ATMB ( No Reversal ) sebagai Acquirer Only dan Acquirer Issuer di Bank Mayapada | Pengujian Done |  |  | 2021-01-28
5 | HSO | ATM Bersama | Sertifikasi | Bank Mayapada | Implementasi Layanan ATMB ( HVT ) di Bank Mayapada | Pengujian Done |  |  | 2021-01-28
6 | AUF | Payment | Sertifikasi | Bank BTN | Implementasi Layanan Payment UI di Bank BTN ( Mitra Tokopedia ) | Monitoring |  |  | 2021-01-28
7 | HMW | ATM Bersama QR | Sertifikasi | Bank Mega Syariah | Implementasi Layanan ATM Bersama QR ( MPM ) sebagai Issuer di Bank Mega Syariah | Pengujian Done |  |  | 2021-01-28
9 | QAH | Payment | Sertifikasi | PT POS | Implementasi Payment Adira ( Biaya Admin Adira Syariah ) di PT POS | Monitoring |  |  | 2021-01-28
10 | AAP | Payment | Sertifikasi | Bank Danamon | Implementasi Payment Adira ( Biaya Admin Adira Syariah ) di Bank Danamon | Project Done |  |  | 2021-01-28
11 | IDO | ATM Bersama | Sertifikasi | Bank BRI Syariah | Implementasi Perbaikan Layanan ATMB ( Crossborder Al Rajhi dan APN ) di BRIS | Pengujian Done |  |  | 2021-01-28
12 | TRH | ATM Bersama Debit | Internal Test | BJB | Internal Test ATMB di Bank BJB | Monitoring |  |  | 2021-01-28
13 | TRH | Laboratory | Sertifikasi | OK! Bank | CPT di OK Bank | Monitoring |  |  | 2021-01-28
14 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Internal Test ATMB ( From/To LinkAja ) di Bank CIMB Niaga | Pengujian Done |  |  | 2021-01-28
15 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test Implementasi ATMB ( Channel EDC ) di Bank Mandiri | Monitoring |  |  | 2021-01-28
16 | RBB | ATM Bersama | Internal Test | Bank Kesejahteraan Ekonomi | Internal Test ATM Bersama Channel Mobile Banking di BKE | Monitoring |  |  | 2021-01-29
18 | AAP | ATM Bersama | Sertifikasi | Bank BTN | Implementasi ATMB ( Penambahan Remark Sistem Internal ) di BTN | Project Done |  |  | 2021-01-29
19 | NSP | Payment | Sertifikasi | PT Jalamaeta Pilar Sinergis | [Regressi]Implementasi Payment ( Indosat Prepaid dan Paket Data ) di Jalameta | Project Done |  |  | 2021-01-29
20 | MAD | ATM Bersama | Sertifikasi | Bank BNI Syariah | Implementasi ATMB ( Merger Bank Syariah Indonesia ) di BNIS | Pengujian Done |  |  | 2021-01-29
21 | AUF | ATM Bersama | Internal Test | Citibank | Internal Test ATMB di Citibank | Monitoring |  |  | 2021-01-29
22 | PDP | ATM Bersama | Internal Test | Bank Sumut | Internal Test ATMB ( Dukungan Aktivasi ATM ) di Bank Sumut | Project Done |  |  | 2021-01-29
23 | DMR | ATM Bersama | Internal Test | Bank Sumut | Internal Test ATMB ( Laku Pandai ) di Bank Sumut | Monitoring |  |  | 2021-01-29
24 | HSO | ATM Bersama QR | Internal Test | OVO | Internal Test ATMB QR ( Enhanchment Sistem Internal ) di Ovo | Project Done |  |  | 2021-01-29
25 | HSO | ATM Bersama | Internal Test | Bank MANTAP | Internal Test ATMB ( Channel Mobile Banking - New SOA ) di Bank Mantap | Project Done |  |  | 2021-01-29
26 | IDE | ATM Bersama Debit | Internal Test | Bank Syariah Mandiri | Internal Test ATMB Debit ( B-Secure ) di BSM | Project Done |  | 100 | 2021-01-29
27 | RAS | Payment | Sertifikasi | Alfamidi | Implementasi Payment ( Indosat Postpaid ) di Alfamidi | Monitoring | 100 | 100 | 2021-01-29
39 | FYS | ATM Bersama | Sertifikasi | Standard Chartered Bank | Implementasi ATMB ( Channel Mobile Banking ) di SCB | Pengujian Done | 100 | 100 | 2021-01-29
40 | MDI | ATM Bersama QR | Internal Test | LinkAja | Internal Test ATMB QR | On Progress |  |  | 2021-01-29
41 | HMW | Payment | Sertifikasi | Bank BPD Bali | Implementasi Payment ( Indosat, XL, Smartfren , Telkomsel, PLN, BPJS, Channel EDC - Artajasa ) di BPD Bali | On Progress |  |  | 2021-01-29
42 | HMW | Payment | Sertifikasi | Bank BPD Bali | Implementasi Payment ( BPD Bali, Channel EDC - Artajasa ) di BPD Bali | On Progress |  |  | 2021-01-29
44 | IDO | ATM Bersama QR | Sertifikasi | Bank Papua | Implementasi ATMB QR ( MPM ) di Bank Papua | Pengujian Done |  |  | 2021-01-29
45 | INA | ATM Bersama QR | Sertifikasi | Bank NTB | Implementasi ATMB QR ( MPM ) di Bank NTB | Pengujian Done | 100 | 100 | 2021-01-29
46 | NSP | Payment | Sertifikasi | Bank Mandiri | [Regressi] Implementasi Payment ( All Payment Existing Mandiri , Update Internal System ) di Bank Mandiri | Hold |  |  | 2021-01-29
47 | AAN | ATM Bersama QR | Sertifikasi | Bank Bengkulu | Implementasi ATMB QR ( MPM ) di Bank Bengkulu | Pengujian Done |  |  | 2021-01-29
49 | AUF | Payment | Sertifikasi | Bank BRI | Implementasi Payment ( PGN, Citibank CC, Prudential, TAF - ESB ) di BRI | Pengujian Done |  |  | 2021-01-29
50 | AUF | ATM Bersama | Sertifikasi | Bank BRI | Implementasi ATMB ( ESB ) di BRI | Pengujian Done |  |  | 2021-01-29
51 | AFH | SDTL Internal System | Internal Project | SDTL | Implementasi SI Koleksi Dokumen (Enhancement Stream 1 - 2021 ) | Project Done |  |  | 2021-01-29
52 | WGH | SDTL Internal System | Internal Project | SDTL | Implementasi SI Koleksi Dokumen (Enhancement Stream 1 - 2021 ) | On Progress |  |  | 2021-01-29
53 | IDE | SDTL Internal System | Internal Project | SDTL | Implementasi SI Koleksi Dokumen (Enhancement Stream 1 - 2021 ) | Project Done |  | 100 | 2021-01-29
54 | HMW | Payment | Internal Test | Bank Mega | Internal Test Payment ( Direct Debit ) di Bank Mega | Pengujian Done |  |  | 2021-01-29
55 | IDE | Payment | Sertifikasi | Bank Bumi Arta | Sertifikasi Payment di BBA | Monitoring | 24.33 |  | 2021-01-29
56 | POK | ATM Bersama | Internal Test | MNC Bank | Internal Test ATMB di MNC | Pengujian Done |  |  | 2021-01-29
57 | QAH | Payment | Sertifikasi | PT Global Digital Niaga Blibli | Implementasi Payment ( PGN ) di BliBli | Monitoring |  |  | 2021-01-29
58 | QAH | Payment | Sertifikasi | Bank Bukopin | Implementasi Payment ( BPJS ) di Bank Bukopin | Drop |  |  | 2021-01-29
59 | MAD | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( XL ) di Bank Papua | Pengujian Done |  |  | 2021-01-29
62 | YKS | ATM Bersama | Sertifikasi | Bank CIMB Niaga | Implementasi ATMB ( CNP ) DI Bank CIMB Niaga | On Progress |  |  | 2021-01-29
65 | TRH | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( Channel CIB ) di Bank Kalsel | Pengujian Done |  |  | 2021-01-29
66 | DFA | SDTL Internal System | Internal Project | Internal | Implementasi Reengineering PBA dan SLA | On Progress |  |  | 2021-01-29
67 | DFA | ATM Bersama QR | Sertifikasi | Rintis | Implementasi ATMB QR ( TTS ) di Rintis | Pengujian Done |  |  | 2021-01-29
68 | AAN | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( PLN, Channel EDC ) di Bank BNI | On Progress |  |  | 2021-01-29
70 | YKS | ATM Bersama QR | Sertifikasi | Mynt | Sertifikasi ATMB QR ( MPM ) di Mynt | Pengujian Done |  |  | 2021-02-01
71 | YKS | SDTL Internal System | Internal Project | Internal | Pendampingan Mahasiswa Magang di SDTL | Project Done |  |  | 2021-02-01
73 | FYS | Payment | Sertifikasi | PT Tokopedia | Implementasi Payment ( TAF ) di Tokopedia | Pengujian Done | 100 | 100 | 2021-02-01
74 | FYS | ATM Bersama | Internal Test | Bank ICBC Indonesia | Internal Test ATMB dan ATMB Debit di ICBC | Pengujian Done | 100 | 100 | 2021-02-01
75 | RBB | ATM Bersama Debit | Sertifikasi | Bank Jago | [Regressi] Implementasi ATMB Debit ( Pendaftaran Prefiks Baru ) di Bank Jago | Pengujian Done |  |  | 2021-02-01
76 | RBB | ATM Bersama | Sertifikasi | Bank Jago | [Regressi] Implementasi ATMB ( Pendaftaran Prefiks Baru ) di Bank Jago | Pengujian Done |  |  | 2021-02-01
77 | RBB | ATM Bersama QR | Sertifikasi | Bank National Nobu | Implementasi ATMB QR ( TTS ) di Bank Nobu | On Progress |  |  | 2021-02-01
81 | EGW | Payment | Internal Project | Internal | Implementasi Sandbox / Test Tool Bersama Payment | Reserve |  |  | 2021-02-01
82 | FYS | Payment | Sertifikasi | BCA Finance | Implementasi Payment ( BCA Finance ) di BCA Finance ( Biller ) | Monitoring | 100 | 95 | 2021-02-01
83 | FYS | Payment | Sertifikasi | PT Tokopedia | Implementasi Payment ( BCA Finance ) di Tokopedia | Monitoring | 100 | 95 | 2021-02-01
84 | RBB | ATM Bersama QR | Sertifikasi | Bank Neo Commerce | Implementasi ATMB QR ( MPM ) Sebagai Issuer di BNC | Pengujian Done | 100 | 68.66 | 2021-02-01
85 | IDE | Payment | Sertifikasi | PT Ayopop Teknologi Indonesia | Implementasi Payment ( Indosat ) di Ayopop | Drop |  |  | 2021-02-01
86 | RMT | SDTL Internal System | Internal Project | SDTL | Implementasi SI Kojes (Enhancement Stream 1 - 2021 ) | Pengujian Done |  |  | 2021-02-01
87 | RMT | ATM Bersama | Internal Test | Bank Sultra | Internal Test ATMB ( Dukungan Pentest ) di Bank Sultra | Monitoring |  |  | 2021-02-01
90 | INA | ATM Bersama QR | Sertifikasi | Jalin | Iplementasi ATMB QR ( TTS ) di Jalin | Pengujian Done | 100 | 100 | 2021-02-01
91 | AAP | Payment | Sertifikasi | Bank Danamon | Implementasi Payment Adira ( Pre Terminasi ) di Bank Danamon | On Progress |  |  | 2021-02-01
94 | TRH | ATM Bersama QR | Internal Test | Bank National Nobu | Internal Test ATMB QR di Bank Nobu | Monitoring |  |  | 2021-02-01
95 | TRH | ATM Bersama | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB ( Merger Bank Syariah Indonesia ) di BSM | On Progress |  |  | 2021-02-01
97 | MWA | ATM Bersama | Sertifikasi | Bank BRI Syariah | Implementasi ATMB ( Merger Bank Syariah Indonesia ) di BRIS | Pengujian Done |  |  | 2021-02-01
98 | MWA | Laboratory | Sertifikasi | Bank Mayora | CPT di Bank Mayora | Pengujian Done |  |  | 2021-02-01
99 | MWA | Laboratory | Sertifikasi | Bank ICBC Indonesia | CPT di Bank ICBC | Pengujian Done |  |  | 2021-02-01
100 | AAP | ATM Bersama QR | Internal Test | Bank BPD Bali | Internal Test ATMB QR di BPD Bali | Monitoring |  |  | 2021-02-01
103 | PDP | ATM Bersama | Sertifikasi | Bank Muamalat | Implementasi ATMB ( Perbaikan Messaging Bit 55 Tag 9C ) di Bank Muamalat | Pengujian Done |  | 100 | 2021-02-01
107 | NSP | ATM Bersama | Internal Test | Bank UOB Indonesia | Internal Test ATMB,ATMB Debit,ATMB QR, dan Payment di UOB | Pengujian Done |  |  | 2021-02-01
108 | AFH | ATM Bersama | Sertifikasi | Bank Sahabat Sampoerna | Implementasi ATMB ( Penyesuaian Channel Internal System ) di BSS | Monitoring |  |  | 2021-02-01
109 | AFH | Payment | Sertifikasi | CV Fifa Multipayment | Implementasi Payment ( Telkomsel Via AJ Pay, Penyesuaian di Finnet ) di FifaPay | Pengujian Done |  |  | 2021-02-01
110 | RAS | ATM Bersama QR | Sertifikasi | Bank Sulut | Implementasi ATMB QR ( MPM ) di Bank SulutGo | Monitoring | 100 | 100 | 2021-02-01
111 | RAS | Payment | Sertifikasi | OVO | Implementasi Payment ( Bersama Top Up ) Sebagai Biller di OVO | Monitoring | 100 | 100 | 2021-02-01
113 | AAN | ATM Bersama QR | Sertifikasi | LinkAja | Implementasi ATMB QR ( TTS ) di LinkAja | Pengujian Done | 97.27 |  | 2021-02-01
114 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test Implementasi ATMB ( Channel EDC ) di Bank Mandiri | On Progress |  |  | 2021-02-01
117 | HSO | ATM Bersama | Internal Test | Bank MANTAP | Internal Test ATMB ( Channel Mobile Banking - New SOA ) di Bank Mantap | Pengujian Done |  |  | 2021-02-01
118 | RAM | Payment | Sertifikasi | Adira | Implementasi Payment ( Adira , Biaya Admin di Adira Syariah ) | Pengujian Done |  |  | 2021-02-01
124 | RAS | Payment | Sertifikasi | Bimasakti | Implementasi Payment ( Bersama Top Up ) di Bimasakti | Monitoring | 100 |  | 2021-02-01
125 | QAH | Payment | Sertifikasi | Adira | Implementasi Payment ( Adira, Pretermination Online ) di Adira | On Progress |  |  | 2021-02-01
126 | QAH | Payment | Sertifikasi | Adira | Implementasi Payment ( Adira, Realtime Notification ) di Adira | On Progress |  |  | 2021-02-01
130 | IDO | ATM Bersama | Internal Test | BPR KS | Internal Test ATMB ( Pengujian Jaringan Backup ) di BPRKS - Bank Mandiri | On Progress |  |  | 2021-02-01
131 | IDO | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( Adira, Pretermitaion Online) di BNI | Reserve |  |  | 2021-02-01
132 | IDO | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( Adira, Biaya Admin) di BNI | Pengujian Done |  |  | 2021-02-01
143 | AUF | Payment | Sertifikasi | Bank BTN | Implementasi Payment ( PGN ) di Bank BTN | Hold |  |  | 2021-02-01
144 | AUF | Payment | Sertifikasi | Bank BTN | Implementasi Payment ( Indosat ) di Bank BTN | Pengujian Done |  |  | 2021-02-01
145 | AUF | SDTL Internal System | Internal Project | SDTL | Implementasi SI Kojes ( Ehancement Stream 1 2021 ) | On Progress |  |  | 2021-02-01
146 | POK | SDTL Internal System | Internal Project | SDTL | Implementasi SI Kojes ( Enhancement Stream 1 2021 ) | On Progress |  |  | 2021-02-01
147 | DMR | SDTL Internal System | Internal Project | SDTL | Implementasi SI Kojes ( Enhancement Stream 1 2021 ) | On Progress |  |  | 2021-02-01
148 | MAD | Payment | Sertifikasi | Bank UOB Indonesia | Implementasi Payment ( Channel MB dan IB ) di Bank UOB | Drop |  |  | 2021-02-01
149 | MAD | Payment | Internal Test | Bank Mestika | Internal Test Payment di Bank Mestika | Project Done |  |  | 2021-02-01
150 | MAD | Payment | Internal Test | Citibank | Internal Test Payment di Citibank | Project Done |  |  | 2021-02-01
151 | MAD | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( Indosat Prepaid dan Paket Data, XL Prepaid dan Paket Data, Channel Laku Pandai ) | On Progress |  |  | 2021-02-01
152 | MAD | ATM Bersama | Internal Test | Bank Papua | Internal Test ATMB ( Dukungan Pengujian Mobile Banking IOS dan Android 11 )di Bank Papua | Project Done |  |  | 2021-02-01
153 | HMW | ATM Bersama | Sertifikasi | BJB | Implementasi ATMB ( Switching Replacement ) di Bank BJB | On Progress |  |  | 2021-02-01
154 | HMW | ATM Bersama Debit | Sertifikasi | BJB | Implementasi ATMB Debit ( Switching Replacement ) di Bank BJB | Pengujian Done |  |  | 2021-02-01
155 | DMR | ATM Bersama | Internal Test | Bank of China Indonesia | Internal Test ATMB dan ATMB Debit | Pengujian Done |  |  | 2021-02-01
156 | DMR | Payment | Sertifikasi | Bank Syariah Mandiri | Implementasi Payment ( Prudential Syariah ) di BSM | Drop |  |  | 2021-02-01
157 | DMR | Payment | Sertifikasi | Bank QNB Indonesia | Implementasi Payment ( Indosat, MNC Group ) di QNB | On Progress |  |  | 2021-02-01
158 | CDE | ATM Bersama | Internal Test | BPR Supra Artapersada/LSB | Internal Test ATMB di BPR Supra | Pengujian Done |  |  | 2021-02-01
159 | WGH | BersamaKU | Sertifikasi | Mynt | Implementasi BersamaKU Mobile | Drop |  |  | 2021-02-01
160 | DFA | ATM Bersama QR | Sertifikasi | Paynet | Implementasi ATMB QR ( Cross Border) di Paynet | On Progress |  |  | 2021-02-01
161 | MMP | ATM Bersama Debit | Internal Test | DSL | Implementasi ATMB Debit ( Suuport Debit 987 ) di DSL | Pengujian Done |  |  | 2021-02-01
162 | WGH | BersamaKU | Sertifikasi | Clickargo | Implementasi BersamaKU ( Disbursement) di Clickargo | Pengujian Done | 100 | 100 | 2021-02-01
163 | WGH | BersamaKU | Internal Test | Home Credit Indonesia | Implementasi BersamaKU ( Disbursement , Perbaikan Signature) di HCI | Monitoring |  |  | 2021-02-01
164 | WGH | ATM Bersama Debit | Internal Test | Fist Payment Indonesia | Implementasi ATMB Debit ( Support 987 Debit ) di First Payment | Drop |  |  | 2021-02-01
165 | HMW | ATM Bersama QR | Sertifikasi | Bank BNI | Implementasi ATMB QR ( MPM ) di BNI | Monitoring | 100 | 100 | 2021-02-01
166 | HMW | ATM Bersama QR | Sertifikasi | Bank Mandiri | Implementasi ATMB QR ( MPM ) di Bank Mandiri | On Progress |  |  | 2021-02-01
167 | INA | ATM Bersama QR | Sertifikasi | Bank Shinhan | Implementasi ATMB QR ( MPM ) di Bank Shinhan | Pengujian Done |  |  | 2021-02-01
168 | INA | ATM Bersama QR | Sertifikasi | Bank Jambi | [Regressi] Implementasi ATMB QR ( MPM , Regressi Update Aplikasi ) di Bank Jambi | Hold |  |  | 2021-02-01
169 | YBP | BersamaKU | Sertifikasi | Koltiva | Implementasi BersamaKU ( Disbursement ) di Koltiva | Pengujian Done |  |  | 2021-02-01
170 | YBP | BersamaKU | Sertifikasi | Bank Papua | Implementasi BersamaKU ( Paid Inquiry) di Bank Papua | On Progress | 100 |  | 2021-02-01
171 | YBP | BersamaKU | Sertifikasi | Adira | Implementasi BersamaKU ( Paid Inquiry) di Adira | Hold |  |  | 2021-02-01
172 | YBP | BersamaKU | Sertifikasi | Bank BRI | Implementasi BersamaKU ( Disbursement ) di BRI | Drop |  |  | 2021-02-01
173 | YBP | BersamaKU | Sertifikasi | BJB | Implementasi BersamaKU ( Disbursement ) di BJB | Drop |  |  | 2021-02-01
174 | YBP | BersamaKU | Sertifikasi | BJB | Implementasi BersamaKU ( Remittance Inbound dan Outbound) di BJB | Drop |  |  | 2021-02-01
175 | MMP | Payment | Sertifikasi | Shopee | Implementasi Payment di Shopee | Pengujian Done |  |  | 2021-02-01
176 | MMP | Payment | Sertifikasi | PT Darmawisata Indonesia | Implementasi Payment ( AJPAY ) di Darmawisata | Pengujian Done |  |  | 2021-02-01
177 | MDI | ATM Bersama QR | Sertifikasi | Dana | Implementasi ATMB QR ( TTS ) di DANA | On Progress |  |  | 2021-02-01
178 | MDI | ATM Bersama QR | Internal Test | Jalin | Implementasi ATMB QR ( CPM , BRI - JALIN ) | Project Done |  |  | 2021-02-01
179 | MDI | Payment | Sertifikasi | Bank BRI | Implementasi Payment ( TAF, Penambahan Field Tenor di Resi ) di BRI | On Progress |  |  | 2021-02-01
180 | MDI | ATM Bersama QR | Sertifikasi | Bank CIMB Niaga | Implementasi ATMB QR ( Cross Border ) di CIMB Niaga | Project Done |  |  | 2021-02-01
181 | MDI | ATM Bersama QR | Sertifikasi | ITMX | Implementasi ATMB QR ( Cross Border) di ITMX | On Progress |  |  | 2021-02-01
183 | MAD | ATM Bersama | Internal Test | Bank Lampung | Internal Test ATMB di Bank Lampung | Project Done |  |  | 2021-02-01
184 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test ATMB ( SOA Biru ) di Bank Mandiri | Monitoring |  |  | 2021-02-01
185 | AAP | Laboratory | Sertifikasi | Cashway | Sertifikasi Terminal di Cashway | Project Done |  |  | 2021-02-02
186 | AAP | Laboratory | Sertifikasi | BPR Danus | CPT di BPR Danus | Project Done |  |  | 2021-02-02
187 | TRH | Laboratory | Sertifikasi | Hyosung | Sertifiasi Terminal di Hyosung | On Progress |  |  | 2021-02-02
188 | MWA | Laboratory | Sertifikasi | Gemalto | Sertifikasi Kartu di Gemalto | Pengujian Done |  |  | 2021-02-02
189 | MWA | Laboratory | Sertifikasi | Feitian | Sertifikasi Terminal di Feitian | Pengujian Done |  |  | 2021-02-02
190 | YBP | BersamaKU | Sertifikasi | Tranglo | Implementasi BersamaKU ( Remittance to Account ) di Tranglo | Drop |  |  | 2021-02-02
191 | MWA | ATM Bersama | Internal Test | Bank Bukopin | Internal Test ATMB ( Cardless Withdrawal ) di Bank Bukopin | Pengujian Done |  |  | 2021-02-02
192 | DMR | ATM Bersama | Internal Test | Bank Sumut | Internal Test ATMB ( Laku Pandai ) di Bank Sumut | Monitoring |  |  | 2021-02-02
193 | LMP | ATM Bersama | Internal Test | Bank Riau Kepri | Internal Test ATMB ( Channel CMS ) di Bank Riau Kepri | Project Done |  |  | 2021-02-02
194 | TRH | Payment | Sertifikasi | Bank BTPN | Implementasi Payment ( Indosat Prepaid dan Postpaid , Channel Jenius Bisnis ) di BTPN | Pengujian Done |  |  | 2021-02-02
195 | HSO | ATM Bersama | Sertifikasi | Bank BPD Kalteng | Implementasi ATMB ( No Reversal Tahap 2 ) di Bank Kalteng | Monitoring | 100 | 90 | 2021-02-02
196 | RBB | ATM Bersama Debit | Sertifikasi | Bank QNB Indonesia | Implementasi ATMB Debit ( Kartu Contactless ) di Bank QNB | Pengujian Done |  |  | 2021-02-02
197 | TRH | Payment | Sertifikasi | Gopay | Implementasi Payment ( CNAF ) di Gopay | On Progress |  |  | 2021-02-02
198 | WGH | ATM Bersama Debit | Internal Test | Multidaya Dinamika | Internal Test ATMB Debit ( Support Debit 987 ) di Multidaya Dinamika | Hold |  |  | 2021-02-03
199 | AUF | ATM Bersama | Internal Test | Citibank | Internal Test ATMB ( Pengujian Temuan Operasional ) di Citibank | Monitoring |  |  | 2021-02-04
200 | LMP | ATM Bersama | Internal Test | ATMI | Internal Test ATMB ( Support ATMB 987 ) di ATMi | Pengujian Done |  |  | 2021-02-04
201 | TRH | ATM Bersama | Internal Project | Internal | Implementasi DB Oracle 19 ( JCB, PLN, Mgate All CA ) | Hold |  |  | 2021-02-04
202 | YBP | BersamaKU | Sertifikasi | Investree | Implementasi BersamaKU ( Disbursement ) di Investree | Pengujian Done | 100 | 100 | 2021-02-04
203 | MWA | Payment | Sertifikasi | Smartfren | Implementasi Payment ( Smartfren Paket Data ) di Smartfren ( As Biller ) | Pengujian Done |  | 40 | 2021-02-05
206 | IDO | ATM Bersama QR | Internal Test | Bank Syariah Mandiri | Internal Test ATMB QR ( MPM ) di BSM | Pengujian Done |  |  | 2021-02-05
207 | MMP | Mynt | Sertifikasi | Anilo | Implementasi Mynt di Anilo | Pengujian Done | 100 | 100 | 2021-02-05
208 | INA | ATM Bersama QR | Sertifikasi | Bank BPD Bali | Implementasi ATMB QR ( Cross Border ) di BPD Bali | Pengujian Done |  |  | 2021-02-05
209 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Implementasi CIMB Regional di CIMB Niaga | On Progress |  |  | 2021-02-05
210 | AFH | Payment | Sertifikasi | Bank Bukopin | Implementasi Payment ( Indosat Paket Data - Penambahan Channel Mobile Banking - Langsung TO ) di Bank Bukopin | Drop |  |  | 2021-02-08
211 | MAD | ATM Bersama | Internal Test | Bank Papua | Implementasi ATMB ( ATMB dan Payment , Dukungan Pengujian Perbaikan Mobile Banking Android ) di Bank Papua | Project Done |  |  | 2021-02-08
212 | WGH | BersamaKU | Sertifikasi | Mynt | Impelementasi BersamaKU ( Bersama Mobile ) di Mynt | Pengujian Done | 100 | 100 | 2021-02-08
213 | YBP | BersamaKU | Sertifikasi | Tranglo | Implementasi BersamaKU ( Remittance to Account ) di Tranglo | Pengujian Done | 100 | 100 | 2021-02-08
214 | RAS | Payment | Sertifikasi | IDS | Implementasi Payment ( IDS - Penyesuaian Spesifikasi ) di IDS ( Sebagai Biller ) | Pengujian Done | 100 | 100 | 2021-02-11
215 | RBB | ATM Bersama Debit | Sertifikasi | Bank Lampung | Implementasi ATMB Debit ( Regressi Sebagai Issuer - dalam rangka pengajuan Izin BI dan OJK ) di Bank Lampung | Pengujian Done |  |  | 2021-02-11
216 | RBB | ATM Bersama Debit | Internal Test | Bank Jago | Internal Test ATMB Debit ( Sebagai Issuer - dalam rangka pengajuan Izin BI dan OJK ) di Bank Jago | Pengujian Done |  |  | 2021-02-11
217 | RAS | ATM Bersama Debit | Sertifikasi | Bank CIMB Niaga | Implemensi ATMB Debit ( Regressi Sistem Internal ) di Bank CIMB Niaga | On Progress | 50 | 50 | 2021-02-11
219 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test ( ATM Bersama - ATM Bersama Debit, SOA Biru ) di Bank Mandiri | On Progress |  |  | 2021-02-15
220 | AAP | Payment | Sertifikasi | Bank Syariah Mandiri | Implementasi Payment ( PGN ) di Bank Syariah Indonesia | Pengujian Done |  |  | 2021-02-22
221 | AAP | ATM Bersama QR | Sertifikasi | Bank Permata | Implementasi ATMB QR ( Crossborder) di Bank Permata | Pengujian Done |  |  | 2021-02-22
222 | PDP | ATM Bersama | Internal Test | Bank Neo Commerce | Implementasi ATM Bersama ( Penambahan CRM ) di Bank BNC | Pengujian Done |  |  | 2021-02-22
224 | MDI | ATM Bersama QR | Internal Test | Bank Ganesha | Internal Test ATMB QR ( MPM ) di Bank Ganesha | Project Done |  |  | 2021-02-22
225 | PDP | Payment | Internal Test | Bank CIMB Niaga | Internal Test Payment ( Indosat Prepaid dan XL Prepaid ) di CIMB Niaga | Drop |  |  | 2021-02-23
226 | POK | Payment | Internal Test | Artajasa (ACQ Only) | Implementasi Payment ( Indosat, Penambahan SOF ) di Aplikasi My IM3 | Monitoring |  |  | 2021-02-23
227 | MMP | Mynt | Sertifikasi | Makara Mas | Implementasi Mynt di Makaramas | Pengujian Done | 100 | 100 | 2021-02-23
228 | YKS | ATM Bersama | Internal Test | LinkAja | Implementasi ATMB ( Update Engine ) di LinkAja | On Progress |  |  | 2021-02-23
229 | IDE | Payment | Internal Test | PT Ayopop Teknologi Indonesia | Implementasi Payment di Ayopop | Monitoring |  | 93.33 | 2021-02-23
230 | MDI | ATM Bersama QR | Sertifikasi | Paynet | Implementasi ATMB QR ( CB ) di Paynet | On Progress |  |  | 2021-02-24
231 | MDI | ATM Bersama QR | Sertifikasi | Dana | Implementasi ATMB QR ( CB ) di Dana | On Progress |  |  | 2021-02-24
232 | RBB | ATM Bersama Debit | Internal Test | Bank Aceh | Internal Test ATMB Debit ( Perizinan BI ) di Bank Aceh | Pengujian Done |  |  | 2021-02-24
233 | IDO | ATM Bersama QR | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB QR ( CB ) di BSI | Pengujian Done |  |  | 2021-02-24
234 | LMP | ATM Bersama Debit | Sertifikasi | Bank BRI Agroniaga | Implementasi ATMB Debit ( Regressi ) di BRI Agro | Pengujian Done |  |  | 2021-02-24
235 | FYS | Payment | Sertifikasi | Mynt | Implementasi Payment ( Bersama Top Up ) di Mynt | Pengujian Done | 100 | 100 | 2021-02-24
236 | TRH | ATM Bersama QR | Sertifikasi | Bank Mayora | Implementasi ATMB QR ( Regressi ) di Bank Mayora | Monitoring |  |  | 2021-02-24
237 | AUF | ATM Bersama | Internal Test | Citibank | Internal Test ATMB ( Perbaikan Isu Operasional ) di Citibank | Pengujian Done |  |  | 2021-02-24
238 | ARE | ATM Bersama QR | Sertifikasi | Citibank | Implementasi ATMB QR ( MPM ) di Citibank | Pengujian Done |  |  | 2021-02-24
239 | ARE | Payment | Sertifikasi | MNC Bank | Implementasi Payment ( Bersama Payment Indosat , XL , Telkomsel ) di MNC | Drop |  |  | 2021-02-24
240 | NSP | ATM Bersama | Internal Test | Bank UOB Indonesia | Internal Test ( ATMB,ATMB Debit, ATMB QR dan Payment ) di Bank UOB | Monitoring |  |  | 2021-03-02
241 | NSP | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( Channel PPOB ) di Bank Lampung | Monitoring |  |  | 2021-03-02
242 | IDO | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN ( Regressi temuan operasional ) di NS3 | Pengujian Done |  |  | 2021-03-02
243 | MAD | ATM Bersama | Internal Test | Bank Papua | Internal Test ATMB ( Support Sertifikasi ATM NSICCS) di Bank Papua | On Progress |  |  | 2021-03-02
244 | YBP | Mynt | Sertifikasi | Koltiva | Implementasi Mynt ( Cobranding ) di Koltiva | Pengujian Done |  | 100 | 2021-03-02
245 | RAM | SDTL Internal System | Internal Project | Internal | Implementasi Pemenuhan Cert Reporting System | On Progress |  |  | 2021-03-02
246 | RAM | ATM Bersama Debit | Sertifikasi | Bank Panin | Implementasi ATMB Debit ( Pengujian MDR ) di Bank Panin | Pengujian Done |  |  | 2021-03-02
247 | RBB | ATM Bersama QR | Sertifikasi | Mareco | Implementasi ATMB QR ( Persiapan Migrasi ) di Mareco | Pengujian Done |  |  | 2021-03-02
248 | TRH | SDTL Internal System | Internal Project | Internal | Implementasi Pemenuhan Cert Reporting System | On Progress |  |  | 2021-03-02
249 | TRH | ATM Bersama QR | Internal Test | Bank National Nobu | Internal Test ATMB QR ( MPM CPM ) di Bank Nobu | Pengujian Done |  | 10 | 2021-03-02
250 | TRH | Laboratory | Sertifikasi | Bank QNB Indonesia | CPT Kartu di Bank QNB | Monitoring |  |  | 2021-03-02
251 | FYS | ATM Bersama | Internal Test | Bank QNB Indonesia | Implementasi ATMB ( BPR Connect - Pengecekan GL ) di Bank QNB | Pengujian Done | 100 | 100 | 2021-03-02
252 | AUF | Payment | Sertifikasi | Bank BTN | Implementasi Payment ( Indosat PPOB ) di Bank BTN | Pengujian Done |  |  | 2021-03-02
253 | AAP | Payment | Sertifikasi | Bank BRI | Implementasi Payment ( Citibank - ESB ) di BRI | Project Done |  |  | 2021-03-02
254 | MWA | Payment | Sertifikasi | XL | Implemetasi Payment XL ( Update Protokol dan IP untuk layanan Paket Data) di XL | Pengujian Done |  |  | 2021-03-02
255 | PDP | ATM Bersama QR | Sertifikasi | Shopee | Implementasi ATMB QR ( MPM ) di Shopee Pay | Pengujian Done | 48 |  | 2021-03-02
256 | IDE | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 2 2021 ) | Monitoring |  |  | 2021-03-08
257 | AFH | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 2 2021 ) | Monitoring |  |  | 2021-03-08
258 | WGH | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 2 2021 ) | Monitoring |  |  | 2021-03-08
259 | RAS | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN ( Regressi Temuan Production ) di NS3 | Monitoring |  |  | 2021-03-08
260 | HSO | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN( Regressi Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-03-08
261 | AFH | Payment | Sertifikasi | Grab Driver | Implementasi Payment ( Bersama Top Up ) di Mitra Grab Driver | Pengujian Done |  |  | 2021-03-08
262 | YKS | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR ( TTS - Penyiapan SVIP Production dan Stress Test ) | Pengujian Done |  |  | 2021-03-08
263 | EGW | ATM Bersama QR | Sertifikasi | Gopay | Implementasi ATMB QR ( Penambahan Header Date ) di Gopay | Pengujian Done |  |  | 2021-03-08
264 | IDO | ATM Bersama | Sertifikasi | Bank DKI | Implementasi ATMB ( Al-Rajhi , Regressi Penambahan Fee ) di Bank DKI | Pengujian Done |  |  | 2021-03-09
265 | NSP | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( Bersama Top Up ) di Bank Lampung | On Progress |  |  | 2021-03-09
266 | MAD | ATM Bersama | Internal Test | Bank Lampung | Internal Test ATMB ( Mobile Banking Baru ) di Bank Lampung | Project Done |  |  | 2021-03-09
267 | RAM | ATM Bersama Debit | Sertifikasi | Bank BNI | Implementasi ATMB Debit ( Master Card ) di BNI | Pengujian Done |  |  | 2021-03-09
268 | FYS | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN ( Regressi Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-03-09
269 | FYS | ATM Bersama QR | Internal Test | Bank Index | Implementasi ATMB QR ( iOS ) di Bank Index | Pengujian Done |  |  | 2021-03-09
270 | MWA | ATM Bersama | Sertifikasi | Bank Bukopin | Implementasi ATMB ( Cardless Withdrawal ) di Bank Bukopin | Pengujian Done |  | 100 | 2021-03-09
271 | ARE | Payment | Internal Test | Gojek | Internal Test PAyment ( BPJS ) di Go Tagihan | Pengujian Done |  |  | 2021-03-09
272 | ARE | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( BPJS Channel Autodebet ) di Bank Kalsel | Pengujian Done |  |  | 2021-03-09
273 | AAP | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN ( Regressi Temuan Production ) di NS3 | Project Done |  |  | 2021-03-09
274 | AAP | ATM Bersama | Sertifikasi | Bank BRI | Implementasi ATMB ( Channel EDC NSICCS ) di BRI | Drop |  |  | 2021-03-09
275 | AAP | Laboratory | Sertifikasi | Bank Panin | CPT Kartu Bank Panin | Pengujian Done |  |  | 2021-03-09
276 | PDP | Payment | Sertifikasi | Bank Mega | Implementasi ayment ( Penambahan Indosat Paket Data di Mobile Banking ) di Bank Mega | Pengujian Done | 50 |  | 2021-03-09
277 | PDP | ATM Bersama Debit | UAT Internal | Internal | Implementasi DBIN ( Regressi Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-03-09
278 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test ATMB ( Channel EDC ) di Bank Mandiri | Pengujian Done |  |  | 2021-03-09
280 | AFH | Payment | Sertifikasi | Bank BPD Bali | Implementasi Payment ( Signal - Samsat Online Nasional ) di CA BPD Bali | Pengujian Done |  |  | 2021-03-22
281 | AFH | Payment | Sertifikasi | Bank Jatim | Implementasi Payment ( Signal - Samsat Online Nasional ) di Biller BPD Jatim | Pengujian Done |  |  | 2021-03-22
282 | IDE | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( Signal - Samsat Online Nasional ) diBiller Bank Lampung | Drop |  |  | 2021-03-22
283 | IDE | Payment | Sertifikasi | Bank Sulteng | Implementasi Payment ( Signal - Samsat Online Nasional ) di CA Bank Sulteng | Drop |  |  | 2021-03-22
284 | RAS | Payment | Sertifikasi | Bank Muamalat | Implementasi Payment ( Bersama Top Up ) di CA Bank Muamalat | Monitoring | 100 | 100 | 2021-03-22
285 | YKS | ATM Bersama QR | UAT Internal | Internal | Penyiapan SVIP CB, BTOP | On Progress |  |  | 2021-03-22
286 | HSO | Payment | Sertifikasi | Bank BPD Bali | Implementasi Payment ( Signal - Samsat Online Nasional ) di Biller BPD Bali | Pengujian Done | 50 |  | 2021-03-22
287 | HSO | Payment | Sertifikasi | Bank Sultra | Implementasi Payment ( Signal - Samsat Online Nasional ) di CA Bank Sultra | Project Done | 50 |  | 2021-03-22
288 | HSO | ATM Bersama QR | Sertifikasi | Bank Jateng | Implementasi ATM Bersama QR ( MPM - Issuer Only ) di Bank Jateng | Pengujian Done | 100 | 100 | 2021-03-22
289 | QAH | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( Signal - Samsat Online Nasional ) di CA Bank Lampung | Reserve |  |  | 2021-03-22
290 | QAH | Payment | Sertifikasi | Bank Nagari | Implementasi Payment ( Signal - Samsat Online Nasional ) di Biller Bank Nagari | Reserve |  |  | 2021-03-22
291 | YKS | ATM Bersama QR | Sertifikasi | Bank BNI | Implementasi ATMB QR ( MPM Acquirer ) di BNI | Reserve |  |  | 2021-03-22
292 | PDP | Payment | Sertifikasi | Bank Bengkulu | Implementasi Payment ( Signal ) di Biller Bank Bengkulu | Pengujian Done |  |  | 2021-03-26
293 | PDP | Payment | Sertifikasi | Bank Maluku | Implementasi Payment ( Signal ) di CA Bank Maluku | On Progress |  |  | 2021-03-26
294 | POK | Payment | Internal Test | Artajasa (ACQ Only) | Implementasi Payment Indosat ( Penambahan SOF ) di My IM3 | Monitoring |  |  | 2021-03-26
295 | POK | ATM Bersama Debit | Sertifikasi | Bank Sumut | Implementasi ATMB Debit ( As Issuer - TO ) di Bank Sumut | Monitoring |  |  | 2021-03-26
296 | PDP | Payment | Sertifikasi | Bank Bengkulu | Implementasi Payment ( Signal ) di CA Bank Bengkulu | On Progress |  | 100 | 2021-03-26
297 | HMW | Payment | Sertifikasi | Bank Maluku | Implementasi Payment ( Signal ) di Biller Bank Maluku | Drop |  |  | 2021-03-26
298 | INA | Payment | Sertifikasi | Alto | Implementasi Payment ( Bersama Top Up ) di CA Alto | Pengujian Done |  |  | 2021-03-26
299 | MMP | Payment | Sertifikasi | Bank Jatim | Implementasi Payment ( Signal ) di CA Bank Jatim | Pengujian Done |  |  | 2021-03-26
300 | MMP | Payment | Sertifikasi | Bank Sulteng | Implementasi Payment ( Signal ) di Biller Bank Sulteng | On Progress |  |  | 2021-03-26
301 | AUF | Payment | Sertifikasi | Bank BTN | Implementasi Payment ( Signal ) di CA BTN | Pengujian Done |  |  | 2021-03-26
302 | AUF | Payment | Sertifikasi | Bank BRI | Implementasi Payment ( Signal ) di CA BRI | Pengujian Done |  |  | 2021-03-26
303 | FYS | Payment | Sertifikasi | Bank Jatim | Implementasi Payment ( Indosat Paket Data dan BPJS Kesehatan - Channel Mobile Banking ) di Bank Jatim | Monitoring | 80 |  | 2021-03-26
304 | ARE | Payment | Internal Test | Bank Panin | Internal Test Payment ( Indosat, CC Citibank - Channel Mobile Banking dan Internet Banking ) di Bank Panin | Pengujian Done |  |  | 2021-03-26
305 | HMW | Payment | Sertifikasi | Bank Nagari | Implementasi Payment ( Signal ) di CA Bank Nagari | On Progress |  | 100 | 2021-03-26
306 | HMW | Payment | Sertifikasi | Bank Sultra | Implementasi Payment ( Signal ) di Biller Bank Sultra | On Progress |  | 100 | 2021-03-26
307 | AAP | Laboratory | Sertifikasi | Vanstone | Sertifikasi Terminal EDC Vanstone | Pengujian Done |  |  | 2021-03-26
308 | AAP | Laboratory | Sertifikasi | Ingenico | Sertifikasi Terminal EDC Ingenico | Pengujian Done |  |  | 2021-03-26
309 | NSP | Payment | Internal Test | Bank Mandiri | Internal Test Payment ( Indosat Paket Data - Channel EDC WSDL ) di Bank Mandiri | Monitoring |  |  | 2021-03-26
310 | MAD | ATM Bersama | Internal Test | Bank BNI Syariah | Internal Test ATMB ( BSI ) di BNIS | Drop |  |  | 2021-03-26
311 | RMT | Payment | Internal Test | Bank NTB | Internal Test Payment ( MBS ) di Bank NTB | On Progress |  |  | 2021-04-07
312 | RMT | Payment | Internal Test | Bank Panin Dubai Syariah | Internal Test Payment ( MBS ) di Bank PDSB | Pengujian Done |  |  | 2021-04-07
313 | RMT | ATM Bersama | Internal Test | Bank Jatim | Internal Test ATMB( Enhancement Internal SMS Banking dan Mobile Banking ) di Bank Jatim | On Progress |  |  | 2021-04-07
316 | RAS | Payment | Sertifikasi | Alfamart | Sertifikasi Payment ( Bersama Billing - IZI ) di Alfamart | Monitoring |  | 100 | 2021-04-07
317 | RAM | Payment | Sertifikasi | Bank DKI | Implementasi Payment ( Signal ) di Biller Bank DKI | On Progress |  |  | 2021-04-07
318 | QAH | Payment | Sertifikasi | Bank DKI | Implementasi Payment ( Signal ) di CA DKI | Reserve |  |  | 2021-04-07
319 | EGW | ATM Bersama QR | Internal Test | Gopay | Internal Test ATMB QR ( MPM , Partial Refund dan Cek Status ) di Gopay | Pengujian Done |  |  | 2021-04-07
320 | PDP | Payment | Sertifikasi | Bank Mandiri | Implementasi Payment ( Signal ) di CA Bank Mandiri | Pengujian Done |  |  | 2021-04-07
321 | POK | ATM Bersama Debit | Sertifikasi | Bank Aceh | Implementasi ATMB Debit ( Issuer - Migrasi dan Tes Oeprasional ) di Bank Aceh | Monitoring |  |  | 2021-04-07
322 | TRH | ATM Bersama Debit | Sertifikasi | Bank DKI | Implementasi ATMB Debit ( B-Secure) di Bank DKI | Monitoring |  |  | 2021-04-07
323 | MWA | OSSW | UAT Internal | Internal | Implementasi OSSW di NS3 | Pengujian Done |  | 74 | 2021-04-07
324 | MWA | Payment | Sertifikasi | Bank BRI Agroniaga | Implementasi Payment ( Bersama Top Up ) di BRI Agro | Pengujian Done |  |  | 2021-04-07
325 | AUF | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( Signal ) di BNI | Pengujian Done |  |  | 2021-04-07
326 | RBB | OSSW | UAT Internal | Internal | Implementasi OSSW di NS3 | On Progress |  |  | 2021-04-07
327 | AAN | OSSW | UAT Internal | Internal | Implementasi OSSW di NS3 | Pengujian Done |  |  | 2021-04-07
328 | IDO | OSSW | UAT Internal | Internal | Implementasi OSSW di NS3 | Pengujian Done |  |  | 2021-04-07
329 | YBP | BersamaKU | Sertifikasi | BJB | Implementasi BersamaKU ( Dusbursement ) di BJB | Reserve |  |  | 2021-04-07
330 | MAD | OSSW | UAT Internal | Internal | Implementasi OSSW di NS3 | Pengujian Done |  |  | 2021-04-07
331 | FYS | ATM Bersama | Internal Test | Bank ICBC Indonesia | Internal Test ATM Bersama di Bank ICBC | Pengujian Done |  |  | 2021-04-20
332 | HSO | Payment | Sertifikasi | Bank NTB | Implementasi Online Payment ( Signal ) di Biller Bank NTB | Pengujian Done |  |  | 2021-04-20
333 | PDP | Payment | Sertifikasi | Bank Papua | Implementasi On;ine Payment ( Signal ) di Biller Bank Papua | On Progress |  |  | 2021-04-20
334 | LMP | ATM Bersama | Sertifikasi | Bank Kalsel | Implementasi ATM Bersama ( Penggantian Switching dan Core Banking ) di Bank Kalsel | On Progress | 100 | 98 | 2021-04-21
335 | RBB | ATM Bersama Debit | Sertifikasi | Bank Kalsel | Implementasi ATM Bersama Debit ( Penggantian Switching dan Core Banking ) di Bank Kalsel | Pengujian Done |  |  | 2021-04-21
336 | MAD | ATM Bersama | Internal Test | Bank Jago | Internal Test ATM Bersama di Bank Jago | Pengujian Done |  |  | 2021-04-21
337 | MAD | Payment | Internal Test | Citibank | Internal Test Payment ( Pemindahan Env UAT ) di Citibank | Project Done |  |  | 2021-04-21
338 | LMP | ATM Bersama Debit | Internal Test | Bank Capital | Internal Test ATMB Debit ( Kelengkapan Dokumen Perizinan ) di Bank Capital | Pengujian Done |  |  | 2021-04-21
339 | RAM | Payment | Sertifikasi | Bank Sulselbar | Implementasi Payment ( Signal ) di CA Bank Sulselbar | Pengujian Done |  |  | 2021-04-21
340 | RAM | Payment | Sertifikasi | Bank Sulselbar | Implementasi Payment ( Signal ) di Bank Sulselbar | Pengujian Done |  |  | 2021-04-21
342 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test ATM Bersama ( Channel EDC, Issuer Bank Mantap ) di Bank Mandiri | Pengujian Done |  |  | 2021-04-21
343 | POK | ATM Bersama Debit | Sertifikasi | Bank Net Syariah | Implementasi ATMB Debit di BNS | Pengujian Done |  |  | 2021-04-21
344 | POK | ATM Bersama QR | Internal Test | Bank Sumut | Internal TEst ATMB QR ( Pentest ) di Bank Sumut | Drop |  |  | 2021-04-21
345 | DMR | ATM Bersama | Internal Test | Bank of China Indonesia | Internal Test ATM Bersama di BOC | Pengujian Done |  |  | 2021-04-21
346 | WGH | Payment | Sertifikasi | BJB | Implementasi Payment ( Signal ) di Biller BJB | On Progress |  | 100 | 2021-04-21
347 | HSO | Payment | Sertifikasi | Bank Jateng | Implementasi Payment ( Signal ) di CA Bank Jateng | Pengujian Done |  | 100 | 2021-04-21
348 | HSO | Payment | Sertifikasi | Bank Jateng | Implementasi Payment ( Signal ) di Biller Bank Jateng | Pengujian Done |  |  | 2021-04-21
350 | RAS | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( PLN Bukopin ) di CA Bank Lampung | Monitoring |  |  | 2021-04-22
351 | RAS | ATM Bersama | Sertifikasi | Artajasa (ACQ Only) | Implementasi ATM Bersama ( Repeat Transfer ) di BKU | Monitoring |  |  | 2021-04-22
352 | RMT | ATM Bersama | Sertifikasi | Bank Riau Kepri | Implementasi ATM Bersama ( Cross Border - Al Rajhi ) di Bank Riau Kepri | Pengujian Done |  |  | 2021-04-22
353 | AFH | Payment | Sertifikasi | Bank Riau Kepri | Implementasi Payment ( Signal ) di Biller Bank Riau Kepri | Pengujian Done |  |  | 2021-04-22
354 | AFH | Payment | Sertifikasi | Bank Riau Kepri | Implementasi Online Payment ( Signal ) di CA Bank Riau Kepri | Pengujian Done |  |  | 2021-04-22
355 | YKS | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR ( MPM CPM dan TTS ) di SVIP | On Progress |  |  | 2021-04-22
356 | MDI | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR ( MPM, CPM dan TTS ) di SVIP | Reserve |  |  | 2021-04-22
357 | EGW | ATM Bersama | Internal Project | Internal | Penyiapan Env Base 24 di NS 3 | Reserve |  |  | 2021-04-22
358 | YBP | BersamaKU | Sertifikasi | Western Union | Implementasi BersamaKU ( Remittance to Account ) di Western Union | Pengujian Done |  |  | 2021-05-04
360 | LMP | ATM Bersama | Sertifikasi | Bank Bengkulu | Sertifikasi ATM Bersama ( Support Development ) di Bank Bengkulu | Pengujian Done |  |  | 2021-05-04
361 | RAM | Payment | Sertifikasi | Bank Jambi | Implementasi Payment ( Signal ) di CA Bank Jambi | Pengujian Done |  |  | 2021-05-04
362 | RAM | Payment | Sertifikasi | Bank Jambi | Sertifikasi Payment ( Signal ) di Biller Bank Jambi | Pengujian Done |  |  | 2021-05-04
363 | IDE | ATM Bersama QR | Sertifikasi | CommonWealth Bank | Implementasi ATMB QR ( MPM as Issuer ) di Bank Commonwealth | Monitoring |  |  | 2021-05-04
365 | RMT | ATM Bersama Debit | Sertifikasi | Bank Jambi | Implementasi ATMB Debit ( Uji Coba Dashboard Transaksi Kartu Debet Bank Jambi ) di Bank Jambi | On Progress |  |  | 2021-05-04
367 | RAS | Payment | Sertifikasi | Bank Mayora | Implementasi Payment ( PGN ) di Bank Mayora | Drop |  |  | 2021-05-04
368 | AAP | ATM Bersama | Sertifikasi | Bank Kesejahteraan Ekonomi | Implementasi ATMB ( Perbaikan Eksepsi ) di BKE | Pengujian Done |  |  | 2021-05-04
369 | AAP | ATM Bersama | Sertifikasi | Bank Net Syariah | Implementasi ATM Bersama di Bank Net Syariah | Pengujian Done |  |  | 2021-05-04
370 | AAP | Laboratory | Sertifikasi | Bank DKI | CPT ( Product 4 dan 5 ) di Bank DKI | Pengujian Done |  |  | 2021-05-04
371 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Implementasi ATMB ( Penggratisan Fee Trx dan MEPS ) di CIMB Niaga | Pengujian Done |  |  | 2021-05-04
372 | INA | ATM Bersama QR | Internal Test | Bank Jambi | Internal Test ATMB QR ( Laku Pandai ) di Bank Jambi | On Progress |  |  | 2021-05-04
373 | DMR | ATM Bersama Debit | Internal Test | Bank Bengkulu | Internal Test ATMB Debit ( Perizinan Debit) di Bank Bengkulu | Pengujian Done |  |  | 2021-05-04
374 | DMR | ATM Bersama | Internal Test | Bank of China Indonesia | Internal Test ATMB di BOC | Pengujian Done |  |  | 2021-05-04
375 | IDE | Payment | Sertifikasi | BPD Kalbar | Implementasi Payment ( Signal ) di Biller Bank Kalbar | Drop |  |  | 2021-05-17
376 | RMT | ATM Bersama | Internal Test | Bank Jago | Internal Test ATM Bersama ( Perbaikan Bit 54 ) di Bank Jago | On Progress |  |  | 2021-05-17
377 | RMT | ATM Bersama | Internal Test | Bank MANTAP | Internal Test ATMB Bersama di Bank Mantap | On Progress |  |  | 2021-05-17
378 | YKS | ATM Bersama QR | Sertifikasi | Bank National Nobu | Implementasi ATMB QR ( Spesifikasi Baru ) di Bank Nobu | Reserve |  |  | 2021-05-17
379 | EGW | ATM Bersama Debit | UAT Internal | Internal | Implementasi ATMB Debit ACQE di NS3 | Reserve |  |  | 2021-05-17
380 | HMW | Payment | Sertifikasi | Bank Mega | Implementasi Direct Debit ( Perubahan FIle Input Balikan ) di Bank Mega | Pengujian Done |  |  | 2021-05-17
381 | AUF | Payment | Sertifikasi | Bank Sulut | Implementasi Payment ( Signal ) di Biller Bank SulutGo | Drop |  |  | 2021-05-17
382 | AAP | BersamaKU | Sertifikasi | Espay ( PT Pembayaran Lintas Usaha Sukses ) | Implementasi BersamaKU ( Disbursement ) di Espay | Drop |  |  | 2021-05-17
383 | IDO | ATM Bersama | Sertifikasi | Bank National Nobu | Implementasi ATM Bersama ( Penggantian Switching ) di Bank Nobu | On Progress |  |  | 2021-05-17
384 | RBB | Payment | Sertifikasi | Bhinneka | Implementasi Payment ( Bersama Billing ) di Bhinneka | Drop |  |  | 2021-05-17
385 | NSP | ATM Bersama | Sertifikasi | Bank UOB Indonesia | Implementasi ATM Bersama ( Open API ) di UOB | Pengujian Done |  |  | 2021-05-17
386 | MAD | ATM Bersama | Internal Test | Bank Lampung | Internal Test ATM Bersama ( Update Apps Mobile Banking ) di Bank Lampung | Project Done |  |  | 2021-05-17
387 | LMP | ATM Bersama | Sertifikasi | Bank Danamon | Pengujian ATM Bersama ( Temuan Operasional - Trx EDC Bank Bukopin ) di Bank Danamon ( Sebagai Issuer ) | Drop |  |  | 2021-05-17
388 | INA | ATM Bersama QR | Sertifikasi | Bank Jambi | Implementasi ATMB QR ( Update Apps iOS ) di Bank Jambi | Hold |  |  | 2021-05-24
389 | INA | ATM Bersama QR | Internal Test | Bank Shinhan | Internal Test ATMB QR ( Support PenTest ) di Bank Shinhan | Pengujian Done |  |  | 2021-05-24
390 | INA | ATM Bersama | Sertifikasi | Bank INA | Implementasi ATMB ( Channel EDC - Artajasa ke Switching Baru ) di Bank INA | On Progress |  |  | 2021-05-24
391 | PDP | Payment | Sertifikasi | Bank Mega | Implementasi Payment ( Indosat Paket Data - Channel ATM ) di Bank Mega | Pengujian Done |  |  | 2021-05-24
392 | PDP | Payment | UAT Internal | Internal | Implementasi MPAY ( Regressi Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-05-24
393 | MMP | Mynt | Sertifikasi | Indivara | Implementasi Mynt ( Bersama Loyalty ) di Indivara | Pengujian Done |  |  | 2021-05-24
394 | MMP | ATM Bersama | Internal Test | BPR Eka | Implementasi ATMB ( Channel ATM - Regressi ) di Bank BPR EKA | Monitoring |  |  | 2021-05-24
395 | POK | ATM Bersama | Sertifikasi | Bank Mega Syariah | Implementasi ATMB ( Perubahan Konfigurasi dan Jaringan ) di BMSI | Drop |  |  | 2021-05-24
396 | POK | ATM Bersama | Internal Test | Bank Danamon | Internal Test ATMB ( JCB ) di Bank Danamon | On Progress |  |  | 2021-05-24
397 | AAN | ATM Bersama Debit | Sertifikasi | Bank Neo Commerce | Implementasi ATMB Debit ( Regressi ) di BNC | Pengujian Done |  |  | 2021-05-24
398 | AAN | ATM Bersama | Internal Test | Bank Mandiri | Internal Test ATMB ( Penambahan JEnis EDC - Mini ATM ) di Bank Mandiri | Pengujian Done |  |  | 2021-05-24
399 | AAN | ATM Bersama | Sertifikasi | Bank Mega | Implementasi ATMB ( Perubahan Konfigurasi - Jaringan ) di Bank Mega | Pengujian Done |  |  | 2021-05-24
400 | RAS | Payment | UAT Internal | Internal | Implementasi Payment ( Regressi Temuan Production MPAY ) di NS3 | Monitoring |  |  | 2021-05-24
401 | HSO | Payment | UAT Internal | Internal | Implementasi Payment ( Regressi Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-05-24
402 | HSO | ATM Bersama | Sertifikasi | Bank BRI Agroniaga | Implementasi ATMB ( Cardless Withdrawal ) di BRI Agro | Pengujian Done | 100 |  | 2021-05-24
403 | RMT | Payment | Internal Test | Bank Papua | Internal Test Payment ( Support UAT MBS ) di Bank Papua | Reserve |  |  | 2021-05-24
404 | EGW | Payment | UAT Internal | Internal | Implementasi Payment ( Perbaikan Temuan Production MPAY ) di NS3 | Reserve |  |  | 2021-05-24
405 | FYS | Payment | UAT Internal | Internal | Implementasi Payment ( Regressi Temuan Production MPAY ) di NS3 | Pengujian Done |  |  | 2021-05-25
406 | FYS | ATM Bersama | UAT Internal | Internal | Implementasi ATMB ( Interkoneksi Regional- MEPS - Update Gapura Stratus ) | Pengujian Done |  |  | 2021-05-25
407 | ARE | ATM Bersama | Internal Test | MNC Bank | Internal Test ATMB di Bank MNC | Pengujian Done |  |  | 2021-05-25
408 | ARE | ATM Bersama | UAT Internal | Internal | Implementasi ATMB ( Interkoneksi Regional - MEPS - Update Gapura Stratus ) | Pengujian Done |  |  | 2021-05-25
409 | AAP | Payment | UAT Internal | Internal | Implementasi Payment ( Perbaikan Temuan Production MPAY ) di NS3 | Project Done |  |  | 2021-05-25
410 | MAD | OSSW | UAT Internal | Internal | Implementasi OSSW Bank INA di NS3 | Drop |  |  | 2021-05-25
411 | IDO | Payment | UAT Internal | Internal | Implementasi Payment ( Perbaikan Temuan Production ) di NS3 | Pengujian Done |  |  | 2021-05-25
412 | NSP | OSSW | UAT Internal | Internal | Implementasi OSSW Bank INA di NS3 | Drop |  |  | 2021-05-25
413 | YBP | BersamaKU | Sertifikasi | Mynt | Implementasi BersamaKU ( Disbursement ) di MYNT | Reserve |  |  | 2021-05-25
414 | LMP | ATM Bersama | Sertifikasi | Bank Kalsel | Implementasi ATMB ( Channel EDC ) di Bank Kalsel | Pengujian Done | 100 | 100 | 2021-05-25
415 | RBB | ATM Bersama | Sertifikasi | Bank Kalsel | Implementasi ATMB ( Channel IB / MB ) di Bank Kalsel | Pengujian Done |  |  | 2021-05-25
416 | AAN | ATM Bersama QR | Internal Test | Bank Lampung | Implementasi ATMB QR ( MPM - Issuer Only ) di Bank Lampung | Pengujian Done |  |  | 2021-06-04
417 | MMP | Payment | UAT Internal | Internal | Implementasi Payment ( Perbaikan M-Gate BNI Agregator ) | Pengujian Done |  |  | 2021-06-04
418 | DFA | Payment | UAT Internal | Internal | Implementasi Payment ( Perbaikan M- Gate BNI Agregator ) | Reserve |  |  | 2021-06-04
419 | WGH | Mynt | Sertifikasi | Mynt | Implementasi Mynt ( Integrasi dengan DIsDukCapil) di Apps Mynt | Pengujian Done | 100 | 100 | 2021-06-04
420 | DMR | ATM Bersama Debit | Internal Test | Internal | Internal Test EDC Android di Artajasa | Monitoring |  |  | 2021-06-04
421 | DMR | ATM Bersama | Sertifikasi | Bank HSBC Indonesia | Implementasi ATMB ( Regressi Internal ) di HSBC | Monitoring |  |  | 2021-06-04
422 | POK | Payment | Internal Test | Artajasa (ACQ Only) | Implementasi Penambahan SOF di My IM3 | On Progress |  |  | 2021-06-04
423 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Internal Test ATMB, ATMB Debit, ATMB QR di CIMB Niaga | Pengujian Done |  |  | 2021-06-04
424 | INA | ATM Bersama Debit | Internal Test | Bank CIMB Niaga | Internal Test ATMB Debit ( Master Card ) di CIMB Niaga | Pengujian Done |  |  | 2021-06-04
425 | IDO | ATM Bersama QR | Internal Test | Bank CIMB Niaga | Internal Test ATMB QR ( Perbaikan Apps untuk Baca QR Crossborder ) di CIMB Niaga | Pengujian Done |  |  | 2021-06-04
426 | MDI | ATM Bersama QR | Sertifikasi | Dana | Implementasi ATMB QR ( Update Spesifikasi JSON ) di DANA | Reserve |  |  | 2021-06-04
427 | NSP | ATM Bersama QR | Internal Test | Bank UOB Indonesia | Internal Test ATMB QR di UOB | Pengujian Done |  |  | 2021-06-04
428 | MAD | ATM Bersama | Internal Test | Bank Neo Commerce | Internal Test ATMB di BNC | On Progress |  |  | 2021-06-04
429 | MAD | Payment | Sertifikasi | Bank UOB Indonesia | Implementasi Payment ( Channel MB dan IB ) di Bank UOB | Drop |  |  | 2021-06-04
430 | ARE | ATM Bersama | Sertifikasi | Bank OCBC NISP | Implementasi ATM Bersama ( Cardless Withdrawal ) di Bank NISP | Hold |  |  | 2021-06-11
431 | MWA | ATM Bersama | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB ( Migrasi Prefiks ) di BSI | Pengujian Done |  |  | 2021-06-11
432 | MWA | Laboratory | Sertifikasi | Bank HSBC Indonesia | CPT di Bank HSBC | Pengujian Done |  |  | 2021-06-11
433 | MWA | Laboratory | Sertifikasi | Bank Sulteng | lCPT di Bank Sulteng | Pengujian Done |  |  | 2021-06-11
434 | MWA | ATM Bersama | Sertifikasi | Bank Permata | Implementasi ATMB ( No Reversal ) di Bank Permata | Hold | 100 | 99 | 2021-06-11
435 | TRH | ATM Bersama QR | Internal Test | Bank Woori Saudara | Internal Test ATMB QR ( Perbaikan Temuan Internal ) di BWS | Pengujian Done |  |  | 2021-06-11
436 | HMW | ATM Bersama QR | Internal Test | Bank BNI | Internal Test ATMB QR ( Penambahan Fitur My QR ) di BNI | Reserve |  |  | 2021-06-11
437 | AAP | ATM Bersama | Sertifikasi | Bank BRI | Implementasi ATM Bersama ( EDC ) di BRI | On Progress |  |  | 2021-06-11
438 | AAP | Laboratory | Sertifikasi | BPR PALU LOKADANA UTAMA | CPT di BPR PALU | Reserve |  |  | 2021-06-11
439 | AAP | Laboratory | Sertifikasi | BPR MODERN EXPRESS | CPT di BPR Modern Express | Reserve |  |  | 2021-06-11
440 | WGH | Payment | Sertifikasi | BJB | Implementasi Payment ( Signal ) di CA Bank BJB | On Progress |  | 100 | 2021-06-11
441 | IDE | ATM Bersama QR | Internal Test | CommonWealth Bank | Internal Test ATMB QR ( Support Pentest ) di CommBank | Reserve |  |  | 2021-06-14
442 | RMT | ATM Bersama | Internal Test | Bank Jago | Internal Test ATMB ( Pengujian Rekening di Core Banking ) di Bank Jago | Reserve |  |  | 2021-06-14
443 | RMT | Payment | Sertifikasi | Bank Jatim | Implementasi Payment ( BPJS, DC Teller ) di Bank Jatim | On Progress |  |  | 2021-06-14
444 | RAS | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( PLN Postpaid , DC MB ) di Bank Lampung | Monitoring | 100 | 100 | 2021-06-14
445 | RAS | Payment | Sertifikasi | Bank Lampung | Implementasi Payment ( PLN NTL , DC MB ) di Bank Lampung | Monitoring | 100 | 100 | 2021-06-14
446 | RAS | ATM Bersama | Sertifikasi | Bank Bukopin | Implementasi ATMB ( Cardless Withdrawal , As Issuer ) di Bank Bukopin | Pengujian Done | 100 | 100 | 2021-06-14
447 | RBB | ATM Bersama | Sertifikasi | Bank Sulut | Implementasi ATMB ( No Reversal ) di Bank SulutGo | On Progress | 100 | 94.68 | 2021-06-17
448 | YBP | Mynt | Sertifikasi | Koltiva | Implementasi Mynt ( Cobranding Fase 2 ) di Koltiva | Pengujian Done |  |  | 2021-06-17
449 | MAD | Payment | Internal Test | Citibank | Internal Test Payment ( Pemindahan Env UAT ) di Citibank | Monitoring |  |  | 2021-06-17
450 | MDI | ATM Bersama QR | Internal Test | Bank National Nobu | Internal Test MPM ( Implementasi UI / Apps Baru ) di Bank Nobu | Reserve |  |  | 2021-06-17
451 | IDO | ATM Bersama QR | Sertifikasi | LinkAja | Implementasi ATMB QR ( Inq MPAN ) di Linkaja | On Progress |  |  | 2021-06-17
452 | HSO | Payment | Internal Test | Bank Bukopin | Internal Test Payment ( Indosat Prepaid, Penyesuaian Denom channel ATM ) di Bank Bukopin | Reserve |  |  | 2021-06-21
453 | HSO | Payment | Internal Test | Bank Bukopin | Internal Test Payment ( Indosat Prepaid, Penyesuaian Denom channel EDC ) di Bank Bukopin | Reserve |  |  | 2021-06-21
454 | IDE | Payment | Sertifikasi | Bank Aceh | Implementasi Payment ( Indosat Prepaid , Channel Mobile Banking ) di Bank Aceh Syariah | On Progress |  |  | 2021-06-21
455 | IDE | Payment | Sertifikasi | Bank Aceh | Implementasi Payment ( Indosat Postpaid , Channel Mobile Banking ) di Bank Aceh Syariah | On Progress |  |  | 2021-06-21
456 | IDE | Payment | Sertifikasi | Bank Aceh | Implementasi Payment ( XL Postpaid , Channel Mobile Banking ) di Bank Aceh Syariah | On Progress |  |  | 2021-06-21
457 | IDE | Payment | Sertifikasi | Bank Aceh | Implementasi Payment ( XL Paket Data , Channel Mobile Banking ) di Bank Aceh Syariah | On Progress |  |  | 2021-06-21
458 | IDE | Payment | Sertifikasi | Bank Aceh | Implementasi Payment ( BPJS Kesehatan , Channel Mobile Banking ) di Bank Aceh Syariah | On Progress |  |  | 2021-06-21
459 | EGW | SDTL Internal System | Internal Project | Internal | Penyiapan Dokumentasi Environement Sertifikasi di SDTL | Reserve |  |  | 2021-06-21
460 | EGW | ATM Bersama QR | Internal Test | Gopay | Implementasi Perubahan Flow Internal di Gopay | Pengujian Done |  |  | 2021-06-21
461 | HMW | Payment | Internal Test | Bank Mega | Internal Test Payment ( Indosat Postpaid ) di Bank Mega | Reserve |  |  | 2021-06-29
462 | ARE | ATM Bersama | Internal Test | MNC Bank | Internal Test ATMB di Bank MNC | Pengujian Done |  |  | 2021-06-29
463 | FYS | ATM Bersama | Sertifikasi | Bank BTPN Syariah | Implementasi ATM Bersama ( New Mobile Banking ) di BTPNS | On Progress |  |  | 2021-06-29
464 | RMT | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( Indosat Prepaid di Delivery Channel IB ) di Bank Papua | On Progress |  |  | 2021-06-29
465 | RMT | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( Indosat Postpaid di Delivery Channel IB ) di Bank Papua | On Progress |  |  | 2021-06-29
466 | FYS | ATM Bersama Debit | Internal Test | Bank ICBC Indonesia | Internal Test ATMB Debit di Bank ICBC | Pengujian Done |  |  | 2021-07-06
467 | AUF | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( BPJS , PLN - Channel ATM, IB ,MB -Migrasi Switching dan CBS ) di Bank Kalsel | On Progress |  |  | 2021-07-06
468 | AUF | ATM Bersama | Sertifikasi | Bank Sulselbar | Implementasi ATM Bersama ( Spesifikasi 4.0.1 ) di Bank Sulselbar | Pengujian Done |  |  | 2021-07-06
469 | HMW | Payment | Sertifikasi | Bank Mandiri | Implementasi Payment ( Indosat Prepaid , Update SOA ) di Bank Mandiri | Reserve |  |  | 2021-07-06
470 | HMW | Payment | Sertifikasi | Bank Mandiri | Implementasi Payment ( Indosat Postpaid, Update SOA ) di Bank Mandiri | Reserve |  |  | 2021-07-06
471 | HMW | Payment | Sertifikasi | Bank Mandiri | Implementasi Payment ( Indosat Paket Data, Update SOA ) di Bank Mandiri | Reserve |  |  | 2021-07-06
472 | TRH | Laboratory | Sertifikasi | Bank Index | CPT di Bank INdex | Monitoring |  |  | 2021-07-06
473 | TRH | Payment | Sertifikasi | Alfamart | Implementasi Payment ( Indosat Postpaid ) di Dan+dan | Pengujian Done |  |  | 2021-07-06
474 | MWA | ATM Bersama | Internal Test | Bank Syariah Mandiri | Implementasi ATMB ( Penyesuaian Limit Transfer) di BSI | Pengujian Done |  |  | 2021-07-06
475 | AAP | Laboratory | Sertifikasi | KONA | Sertifikasi Kartu di KONA | Pengujian Done |  |  | 2021-07-06
476 | MAD | ATM Bersama QR | Sertifikasi | Bank Kalsel | Implementasi ATMB QR ( MPM ) di Bank Kalsel | Reserve |  |  | 2021-07-06
477 | NSP | ATM Bersama | Internal Test | Bank UOB Indonesia | Internal Tes Pemindahan Koneksi antara Artajasa dan Bank UOB | Pengujian Done |  |  | 2021-07-06
478 | NSP | Payment | Sertifikasi | Bank Syariah Mandiri | Implementasi Payment ( regressi Payment Indosat ) di BSI | Monitoring |  |  | 2021-07-06
479 | NSP | ATM Bersama | Internal Test | IMKAS | Internal Test ATMB QR di IMKAS | Monitoring |  |  | 2021-07-06
480 | RBB | ATM Bersama | Sertifikasi | Bank Kesejahteraan Ekonomi | Implementasi ATMB ( Spek 4.0 ) di BKE ( SEA BANK ) | Drop |  |  | 2021-07-06
481 | LMP | Mynt | Sertifikasi | PT Ciwaru Transaksi Elektronis | Implementasi Mynt Cobranding di PT Ciwaru Transaksi Elektronis | Pengujian Done | 100 | 100 | 2021-07-06
482 | IDO | ATM Bersama QR | Sertifikasi | Bank Papua | Implementasi ATMB QR ( Migrasi dan TO ) di Bank Papua | Monitoring |  |  | 2021-07-06
483 | DMR | ATM Bersama | Internal Test | BPR Eka | Implementasi ATMB ( Channel EDC ) di BPR EKA | Reserve |  |  | 2021-07-06
484 | AAN | ATM Bersama | Internal Test | Bank Syariah Mandiri | Internal Test ATMB ( Acq Bank Mandiri ) di BSI | Pengujian Done |  |  | 2021-07-06
485 | POK | Payment | Internal Test | Artajasa (ACQ Only) | Implementasi Payment ( Indosat ) di Channel Whatsapp Chatbot | On Progress |  |  | 2021-07-06
486 | POK | Payment | Internal Test | Bank Sinarmas | Internal Test Payment ( Indosat ) di Bank Sinarmas | Pengujian Done |  |  | 2021-07-06
487 | MMP | BersamaKU | UAT Internal | Internal | Implementasi BersamaKU ( Perubahan BRI Direct ) | Pengujian Done |  |  | 2021-07-06
488 | MMP | Payment | Internal Test | Shopee | Internal Test Payment ( Bersama Billing ) di Shopee | Pengujian Done |  |  | 2021-07-06
489 | INA | Payment | Sertifikasi | Alto | Implementasi Payment ( Bersama TOp Up Ovo - Biaya Admin ) di Alto | On Progress |  |  | 2021-07-06
490 | RMT | Payment | Internal Test | Bank Papua | Internal Test ( Perbaikan Hasil UAT Webtools Mobile Banking Bank Papua ) | Pengujian Done |  |  | 2021-07-06
491 | RMT | Payment | Internal Test | Bank Papua | Internal Test ( Perbaikan Hasil UAT Webtools SMS Banking Bank Papua ) | Pengujian Done |  |  | 2021-07-06
492 | RMT | Payment | Internal Test | Bank Papua | Internal Test ( Perbaikan Hasil UAT APK Mobile Banking Bank Papua ) | Pengujian Done |  |  | 2021-07-06
493 | RAS | Payment | Sertifikasi | Bimasakti | Implementasi Payment ( Bersama Top Up OVO - Biaya Admin ) di BimaSakti | Reserve | 100 | 100 | 2021-07-06
494 | RAS | Payment | Sertifikasi | Smartfren | Implementasi Payment ( Smartfren Paket Data - E2E ) di Smartfren | Pengujian Done | 100 | 100 | 2021-07-06
495 | POK | Payment | Sertifikasi | Bank QNB Indonesia | Implementasi Payment ( Indosat Prepaid - Mobile Banking ) di Bank QNB | Pengujian Done |  |  | 2021-07-14
496 | POK | Payment | Sertifikasi | Bank QNB Indonesia | Implementasi Payment ( Indosat Postpaid - Mobile Banking ) di Bank QNB | Pengujian Done |  |  | 2021-07-14
497 | POK | Payment | Sertifikasi | Bank QNB Indonesia | Implementasi Payment ( MNC Play - Mobile Banking ) di Bank QNB | Pengujian Done |  |  | 2021-07-14
498 | POK | Payment | Sertifikasi | Bank QNB Indonesia | Implementasi Payment ( Indovision/Top TV/OK TV - Mobile Banking ) di Bank QNB | Pengujian Done |  |  | 2021-07-14
499 | INA | ATM Bersama QR | Sertifikasi | Bank BPD Bali | Implementasi ATMB QR ( Perbaikan Temuan Production ) di BPD Bali | Pengujian Done |  |  | 2021-07-14
500 | INA | Payment | Sertifikasi | Bank CIMB Niaga | Implementasi Payment ( Smartfren Paket Data ) di Bank CIMB Niaga | On Progress |  |  | 2021-07-14
502 | QAH | BersamaKU | Internal Test | Home Credit Indonesia | Internal Test BersamaKU ( Disbursement ) di HCI | Reserve |  |  | 2021-07-15
503 | YKS | ATM Bersama QR | Sertifikasi | Bank National Nobu | Implementasi ATMB QR ( Resertifikasi karena Perubahan Sistem ) di Bank Nobu | Reserve |  |  | 2021-07-15
504 | TRH | Laboratory | Sertifikasi | Bank Sultra | CPT Bank Sultra | Monitoring |  |  | 2021-07-16
505 | AAP | ATM Bersama | Internal Test | Bank Kesejahteraan Ekonomi | Implementasi ATMB ( SFTP report ) di SEA Bank | On Progress |  |  | 2021-07-16
506 | MWA | Laboratory | Sertifikasi | NCR | Sertifikasi Terminal ATM NCR | Pengujian Done |  |  | 2021-07-16
507 | HSO | ATM Bersama | Internal Test | Bank BPD Kalteng | Internal Test ATMB ( Channel LakuPandai) di Bank Kalteng | Pengujian Done |  |  | 2021-07-27
508 | HSO | Payment | UAT Internal | Alfamart | Regressi Gapura Alfamart - Mgate All CA untuk CA Alfamart | On Progress |  |  | 2021-07-27
509 | HSO | Payment | Sertifikasi | PT Eratel Prima | Sertifikasi Payment ( Bersama Top Up Ovo ) di CA Eratel | On Progress |  |  | 2021-07-27
510 | RAS | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR di SVIP | Pengujian Done |  |  | 2021-07-27
511 | RAS | ATM Bersama | Sertifikasi | Bank Bumi Arta | Regressi ATMB ( Payment Kartu Kredit Via Transfer ) di BBA | Pengujian Done |  | 100 | 2021-07-27
512 | QAH | Payment | Internal Test | Bank NTB | Support Pengembangan Payment ( Signal ) di CA Bank NTB | On Progress |  |  | 2021-07-27
513 | YKS | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR di SVIP | On Progress |  |  | 2021-07-27
514 | EGW | SDTL Internal System | UAT Internal | Internal | Pemindahan Server SDTL ke Host VM Lintasarta | On Progress |  |  | 2021-07-27
515 | EGW | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR di SVIP | On Progress |  |  | 2021-07-27
516 | FYS | Payment | Internal Test | OVO | Internal Test ATMB QR di OVO | Reserve |  |  | 2021-07-27
517 | TRH | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR di SVIP | On Progress |  |  | 2021-07-27
518 | TRH | ATM Bersama Debit | Sertifikasi | Bank OCBC NISP | Implementasi ATMB Debit ( Master Card ) di OCBC NISP | Pengujian Done |  |  | 2021-07-27
519 | HMW | Payment | Internal Test | Artajasa (ACQ Only) | Regressi Payment ( Autodebet Artajasa ) | Monitoring |  |  | 2021-07-27
520 | ARE | Payment | Internal Test | Bank Panin | Internal Test Payment di Bank Panin | Pengujian Done |  |  | 2021-07-27
522 | DMR | ATM Bersama | Internal Test | Bank of China Indonesia | Internal Test ATMB ( Termasuk ATMB debit ) di BOC | Reserve |  |  | 2021-07-29
523 | AAN | Payment | Sertifikasi | Indosmart Komunikasi Global | Implementasi Payment ( Bersama Top Up - OVO ) di CA Indosamart | Pengujian Done |  |  | 2021-07-29
524 | AAN | ATM Bersama QR | Sertifikasi | Bank Lampung | Implementasi ATMB QR ( MPM as Issuer ) di Bank Lampung | Pengujian Done |  |  | 2021-07-29
525 | POK | Payment | Internal Test | Artajasa (ACQ Only) | Implementasi Penambahan SOF di My IM3 | Monitoring |  |  | 2021-07-29
526 | POK | ATM Bersama | Internal Test | Bank Danamon | Internal Test ATMB ( Pembayaran Kartu Kredit Via IBFT Pada Channel MB ) di Bank Danamon | Drop |  |  | 2021-07-29
527 | DFA | ATM Bersama QR | Sertifikasi | ITMX | Implementasi ATMB QR ( Cross Border) di ITMX | On Progress |  |  | 2021-07-29
528 | NSP | ATM Bersama | Internal Test | Bank UOB Indonesia | Internal Test ATMB ( ATMB Debit ) di UOB | On Progress |  |  | 2021-07-29
529 | MDI | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR di SVIP | On Progress |  |  | 2021-07-29
530 | MAD | Payment | Internal Test | CommonWealth Bank | Internal Test dan Support Pengembangan Payment di Bank Commonwealth | Reserve |  |  | 2021-08-16
531 | PDP | ATM Bersama | UAT Internal | Internal | Implementasi No Reversal di Acq BICI dan Implementasi STAN Up to 999999 di ATMB | Pengujian Done |  |  | 2021-08-16
532 | POK | ATM Bersama | Sertifikasi | Allo Bank | Implementasi ATM Bersama di Allo Bank | Pengujian Done |  |  | 2021-08-16
533 | LMP | ATM Bersama | Internal Test | Bank Jatim | Internal Test ATM Bersama ( Support UAT Transfer Issuer-Destination ) di Bank Jatim | Pengujian Done |  |  | 2021-08-16
534 | MWA | ATM Bersama QR | UAT Internal | Internal | Implementasi Penambahan Key Base24 untuk Pengecekan respon trx di Env DBIN | Pengujian Done |  |  | 2021-08-16
535 | LMP | ATM Bersama | Internal Test | Bank of China Indonesia | Internal Test ATM Bersama di BOC | Pengujian Done |  |  | 2021-08-16
536 | DMR | Payment | Sertifikasi | Arindo | Implementasi Payment ( Bersama Top Up ) di Arindo | On Progress |  |  | 2021-08-16
537 | YBP | Payment | Sertifikasi | Hotel Murah | Implementasi Payment ( Bersama Top Up ) di Hotel Murah | On Progress |  |  | 2021-08-16
538 | RBB | Payment | Sertifikasi | Bank NTT | Impplementasi Payment ( FIF ) di Bank NTT | Drop |  |  | 2021-08-16
539 | AFH | ATM Bersama QR | Sertifikasi | Bank Papua | Implementasi ATMB QR ( MPM as Acquirer Laku Pandai ) di Bank Papua | On Progress |  |  | 2021-08-16
540 | WGH | Payment | Sertifikasi | PT Design Jaya Indonesia | Impplementasi Payment ( Bersama Top Up ) di DJI | On Progress | 100 | 100 | 2021-08-16
541 | YBP | BersamaKU | Sertifikasi | Midtrans | Implementasi BersamaKU ( Paid Inquiry ) di Midtrans | Pengujian Done | 100 | 100 | 2021-08-16
542 | IDE | ATM Bersama QR | Internal Test | CommonWealth Bank | Internal Test ATMB QR di Bank Commonwealth | Monitoring |  |  | 2021-08-16
543 | HSO | Payment | Sertifikasi | Gojek | Implementasi Payment ( Adira ) di Gojek | On Progress |  |  | 2021-08-16
544 | PDP | ATM Bersama | Sertifikasi | BJB | Implementasi ATM Bersama ( Cardless Withdrawal ) di BJB | On Progress |  |  | 2021-08-16
545 | IDO | ATM Bersama | Sertifikasi | BPR KS | Implementasi ATM Bersama ( Perbaikan Bit 55 ) di BPR KS | Pengujian Done |  |  | 2021-08-16
546 | RBB | ATM Bersama Debit | Internal Test | Bank Papua | Internal Test ATM Bersama Debit ( As Acquirer ) di Bank Papua | Pengujian Done |  |  | 2021-08-16
547 | IDO | ATM Bersama | Sertifikasi | Bank DKI | Implementasi ATM Bersama Cross Border ( Al rajhi - Resertifikasi Format 2 ) di Bank DKI | On Progress |  |  | 2021-08-16
548 | MWA | ATM Bersama QR | Sertifikasi | Bank Muamalat | Implementasi ATMB QR ( MPM as Acquirer ) di Bank Muamalat | Pengujian Done |  |  | 2021-08-16
549 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Internal Test CIMB Regional | Monitoring |  |  | 2021-08-26
550 | INA | ATM Bersama | Internal Test | Bank CIMB Niaga | Internal Test ATMB dan ATMB Debit untuk Emboss Kartu baru Master Card di CIMB Niaga | Monitoring |  |  | 2021-08-26
551 | INA | ATM Bersama QR | Internal Test | Bank Shinhan | Internal Test ATMB QR ( perbaikan Temuan ASPI ) di Bank Shinhan | On Progress |  |  | 2021-08-26
552 | INA | ATM Bersama QR | Internal Test | Bank NTB | Internal Test ATMB QR ( Regressi Debit Kredit Persiapan Live ) di Bank NTB | Monitoring |  |  | 2021-08-26
553 | INA | ATM Bersama QR | UAT Internal | Internal | Implementasi Additional Key for DBIN ( STAN ) di Base24 | On Progress |  |  | 2021-08-26
554 | DFA | ATM Bersama | Sertifikasi | Bank BNI | Implementasi ATMB ( Platform Jalin ) di BNI | On Progress |  |  | 2021-08-26
555 | RMT | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( PLN Prepaid Channel Lakupandai ) di Bank Papua | On Progress |  |  | 2021-08-26
556 | RMT | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( PLN Postpaid Channel Lakupandai ) di Bank Papua | On Progress |  |  | 2021-08-26
557 | RMT | Payment | Sertifikasi | Bank Papua | Implementasi Payment ( PLN NTL Channel Lakupandai ) di Bank Papua | On Progress |  |  | 2021-08-26
558 | RAS | ATM Bersama QR | Sertifikasi | BJB | Implementasi ATMB QR ( MPM as Acquirer dan Issuer ) di BJB | Pengujian Done | 100 | 100 | 2021-08-26
559 | RAS | ATM Bersama QR | Internal Test | Bank NTT | Internal Test ATMB QR di Bank NTT | Monitoring | 100 | 100 | 2021-08-26
560 | AFH | Payment | Internal Test | Bank Bukopin | Internal Test Payment ( Indosat Prepaid - Perubahan Denom Indosat ) di Bank Bukopin | Pengujian Done |  |  | 2021-08-26
561 | HSO | ATM Bersama QR | Internal Test | Bank Jateng | Internal Test ATMB QR di Bank Jateng | Pengujian Done |  |  | 2021-08-26
562 | QAH | BersamaKU | Sertifikasi | PT. Sarana Pactindo | Implementasi BersamaKU ( Disbursement ) di PAC | On Progress |  |  | 2021-08-26
563 | QAH | Payment | Sertifikasi | PT. Enigma | Implementasi Payment ( Bersama Top Up ) di Enigma | Reserve |  |  | 2021-08-26
564 | FYS | ATM Bersama | UAT Internal | Internal | Implementasi No Reversal BICI Acq ( Regressi ) Base24 di ATMB | Monitoring |  |  | 2021-08-27
565 | FYS | ATM Bersama | Internal Test | Bank BTPN Syariah | Internal Test ( Regressi ) di BTPNS | Reserve |  |  | 2021-08-27
566 | TRH | Payment | Sertifikasi | Bank BTPN | Implementasi Perbaikan temuan Indosat Postpaid di BTPN | Pengujian Done |  |  | 2021-08-27
567 | TRH | Laboratory | Sertifikasi | Vanstone | Sertifikasi Terminal di Vanstone | Monitoring |  |  | 2021-08-27
568 | TRH | Payment | Sertifikasi | Bank BTN | Implementasi ATMB ( Platform Jalin ) di BTN | Hold |  |  | 2021-08-27
569 | MWA | ATM Bersama | Internal Test | Bank Syariah Mandiri | Internal Test ATMB ( Perubahan Limit di Channel CMS ) di BSI | Pengujian Done |  |  | 2021-08-27
570 | MWA | Laboratory | Sertifikasi | Bank Net Syariah | CPT di Bank Net Syariah ( Bank Aladin Syariah ) | Pengujian Done |  |  | 2021-08-27
571 | MWA | Payment | Sertifikasi | Bank BRI Agroniaga | Implementasi Payment ( Bersama Top Up - Perubahan Biaya Admin OVO ) di BRI Agro | Monitoring |  |  | 2021-08-27
572 | ARE | ATM Bersama QR | UAT Internal | Internal | Implementasi Additional Key for DBIN ( STAN ) di Base24 | Pengujian Done |  |  | 2021-08-27
573 | AUF | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( Signal Channel ATM ) di BNI | Pengujian Done |  |  | 2021-08-27
574 | AAP | ATM Bersama QR | UAT Internal | Internal | Implementasi Additional Key for DBIN ( STAN ) di Base24 | Pengujian Done |  |  | 2021-08-27
575 | AAP | Laboratory | Sertifikasi | Bank Panin | CPT Kartu di Bank Panin | Pengujian Done |  |  | 2021-08-27
576 | MAD | ATM Bersama | Internal Test | IMKAS | Internal Test ATMB | Reserve |  |  | 2021-08-27
577 | EGW | ATM Bersama Debit | UAT Internal | Internal | Implementasi ATMB Debit ( CSM Test ) di NS3 | Reserve |  |  | 2021-09-17
578 | CDE | ATM Bersama | Internal Test | BJB | Internal Test ATMB ( Perubahan Switching ) di Bank BJB | Reserve |  |  | 2021-09-17
579 | CDE | ATM Bersama Debit | Internal Test | BJB | Internal Test ATMB Debit ( Perubahan Switching ) di Bank BJB | Reserve |  |  | 2021-09-17
580 | PDP | ATM Bersama | Sertifikasi | Bank Mandiri | Implementasi ATM Bersama ( Jalin sebagai ATM Controller ) di Bank Mandiri | Reserve |  |  | 2021-09-24
581 | AUF | Payment | Sertifikasi | Bank BNI | Implementasi Payment ( Penambahan Channel SMS Banking - Signal ) di Bank BNI | On Progress |  |  | 2021-09-24
582 | IDO | ATM Bersama | Sertifikasi | Artajasa (ACQ Only) | Implementasi ATM Bersama ( BPR Ware - Bank Mandiri ) di Artajasa | Reserve |  |  | 2021-09-24
583 | LMP | ATM Bersama | Internal Test | Bank DKI | Internal Test ATM Bersama ( Perbaikan Temuan Operasional - Bit 55 ) di Bank DKI | On Progress |  |  | 2021-09-24
584 | MAD | ATM Bersama QR | Internal Test | IMKAS | Internal test ATMB QR di IMKAS | Reserve |  |  | 2021-09-24
585 | MAD | ATM Bersama QR | Internal Test | IMKAS | Internal test ATMB QR di IMKAS | Reserve |  |  | 2021-09-24
586 | TRH | Payment | Internal Test | Bank BTPN | Internal Test Payment ( Indosat Prepaid ) di BTPN | Pengujian Done |  |  | 2021-09-27
587 | TRH | ATM Bersama Debit | Sertifikasi | Bank National Nobu | Implementasi ATMB Debit ( Migrasi Routing ke Master Card ) di Bank Nobu | Pengujian Done |  |  | 2021-09-27
588 | TRH | Laboratory | Sertifikasi | Standard Chartered Bank | CPT di SCB | Pengujian Done |  |  | 2021-09-27
589 | TRH | ATM Bersama QR | UAT Internal | Internal | Regressi ATMB QR ( Validasi Cek Status terhadap Transaksi Payment ) di Base 24 | Monitoring |  |  | 2021-09-27
590 | TRH | Laboratory | Sertifikasi | PAX | Sertifikasi Terminal PAX | Reserve |  |  | 2021-09-27
591 | ARE | ATM Bersama | Internal Test | Citibank | Internal Test ATM Bersama ( Regressi ) di Citibank | Pengujian Done |  |  | 2021-10-04
592 | ARE | ATM Bersama QR | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB QR ( CPM ) di BSI | Drop |  |  | 2021-10-04
593 | ARE | ATM Bersama | Internal Test | Bank Kesejahteraan Ekonomi | Internal Test ATM Bersama ( Support Stress Test ) di SEABank | Drop |  |  | 2021-10-04
594 | ARE | ATM Bersama | Sertifikasi | Bank BRI | Implementasi ATM Bersama ( Acquirer Platform Jalin ) di BRI | Reserve |  |  | 2021-10-04
595 | ARE | Payment | UAT Internal | Internal | UAT Internal Payment ( Indosat Paket Data - Enhance M Gate BCA) | Reserve |  |  | 2021-10-04
596 | ARE | ATM Bersama QR | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB QR ( Dynamic QR as Acquqirer MPM ) di BSI | Pengujian Done |  |  | 2021-10-04
597 | EGW | ATM Bersama | UAT Internal | Internal | Penyiapan Skenario dan Pelaksanaan BCP Artajasa | Reserve |  |  | 2021-10-04
599 | YKS | ATM Bersama | UAT Internal | Internal | Penyiapan Skenario dan Pelaksanaan BCP Artajasa | Reserve |  |  | 2021-10-04
600 | DFA | ATM Bersama | UAT Internal | Internal | Penyiapan Skenario dan Pelaksanaan BCP Artajasa | Reserve |  |  | 2021-10-04
601 | YKS | ATM Bersama QR | Sertifikasi | Bank BNI | Implementasi ATMB QR ( TTS ) di BNI | Reserve |  |  | 2021-10-04
602 | AAP | Laboratory | Sertifikasi | BPR Irian | CPT BPR Irian Sentosa | Reserve |  |  | 2021-10-04
603 | AAP | ATM Bersama | Sertifikasi | Bank AGRIS | Sertifikasi ATM Bersama ( Penambahan Channel IB dan MB ) di IBK | Reserve |  |  | 2021-10-04
604 | MDI | ATM Bersama | Sertifikasi | BPD Kalbar | Implementasi ATM B ( Resertifikasi Spek 4.0 ) di Bank Kalbar | On Progress |  |  | 2021-10-04
605 | AAN | ATM Bersama Debit | Sertifikasi | Bank BPD Bali | Sertifikasi ATM Debit ( as Acquirer ) di BPD Bali | Reserve |  |  | 2021-10-04
606 | AAN | ATM Bersama | Sertifikasi | Bank Banten | Implementasi ATM Bersama ( Resertifikasi Spek 4.0 ) di Bank Banten | On Progress |  |  | 2021-10-04
607 | AAN | Payment | Internal Test | Bank BNI | Internal Test Payment ( PLN Postpaid - Penambahan ATM Platform Jalin ) di BNI | On Progress |  |  | 2021-10-04
608 | RBB | ATM Bersama Debit | Sertifikasi | Bank Sahabat Sampoerna | Implementasi ATMB Debit ( Penambahan Koneksi untuk Kartu VISA ) di BSS | On Progress | 14.29 |  | 2021-10-04
609 | LMP | ATM Bersama Debit | Internal Test | Bank BRI Agroniaga | Implementasi ATMB Debit ( Support Pengujian Report / SFTP ) di BRI Agro | Monitoring |  |  | 2021-10-04
610 | LMP | Payment | Sertifikasi | Bank CIMB Niaga | Implementasi Payment ( PGN ) di CIMB Niaga | On Progress |  |  | 2021-10-04
611 | LMP | ATM Bersama | Internal Test | Bank CIMB Niaga | Internal Test ATMB ( Regressi ATMB / MEPS / CIMB Regional ) di CIMB Niaga | On Progress |  |  | 2021-10-04
612 | DMR | ATM Bersama | Internal Test | Bank HSBC Indonesia | Internal Test ATM Bersama ( regressi kebutuhan internal ) di HSBC | On Progress |  |  | 2021-10-04
613 | TRH | ATM Bersama QR | UAT Internal | Internal | Implementasi ATMB QR ( CPM - Bansos ) | Reserve |  |  | 2021-10-04
614 | IDO | ATM Bersama QR | Sertifikasi | LinkAja | Implementasi ATMB QR ( CPM - Bansos ) di LA | Reserve |  |  | 2021-10-04
615 | MWA | ATM Bersama | Sertifikasi | Bank Sahabat Sampoerna | Implementasi ATM Bersama ( Acq Iss HVT dan VISA ) di BSS | On Progress |  |  | 2021-10-04
616 | MWA | Laboratory | Sertifikasi | Bank Capital | CPT di Bank Capital | Monitoring |  |  | 2021-10-04
617 | MWA | Laboratory | Sertifikasi | Feitian | Sertifikasi Terminal di Feitian | Monitoring |  |  | 2021-10-04
618 | MWA | Laboratory | Sertifikasi | Fujian Newland | Sertifikasi Terminal di Fujian Newland | On Progress |  |  | 2021-10-04
619 | AFH | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 3 2021 ) | On Progress |  |  | 2021-10-04
620 | AFH | Payment | Sertifikasi | Bank Syariah Mandiri | Implementasi Payment ( Signal ) di BSI | On Progress |  |  | 2021-10-04
621 | AFH | Payment | Sertifikasi | Bank Bukopin | Implementasi Payment ( Indosat Paket Data - Penambahan Channel MB ) di KB Bukopin | Reserve |  |  | 2021-10-04
622 | IDE | Payment | Sertifikasi | Bank BTPN Syariah | Implementasi Payment ( SW Hulu ) di BTPNS | On Progress |  |  | 2021-10-04
623 | IDE | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 3 2021 ) | On Progress |  |  | 2021-10-04
624 | RAS | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( PLN - Resertifikasi Ganti Switching ) di Bank Kalsel | Pengujian Done |  |  | 2021-10-04
625 | HSO | Payment | Sertifikasi | Artajasa (ACQ Only) | Implementasi Payment ( Bersama Top Up ) di CA BersamaKU | Reserve |  |  | 2021-10-04
626 | NSP | Payment | Sertifikasi | Bank Mandiri | Implmentasi Payment ( Perbaikan Gapura WSDL Mandiri ) di Bank Mandiri | On Progress |  |  | 2021-10-04
627 | NSP | Payment | Sertifikasi | Bank Lampung | Sertifikasi Payment ( Telkomsel Postpaid ) di Bank Lampung | On Progress |  |  | 2021-10-04
628 | HMW | ATM Bersama | Internal Test | Artajasa (ACQ Only) | Internal Test ATM Bersama ( Regressi Acq 987 ) | Reserve |  |  | 2021-10-04
629 | WGH | SDTL Internal System | Internal Project | Internal | Implementasi SI Koleksi Dokumen ( Enhanchment Phase 3 2021 ) | On Progress |  |  | 2021-10-04
630 | YBP | Mynt | Sertifikasi | Koltiva | Implementasi Mynt ( Penambahan Fitur Transfer Merchant ke Member dan Purchase ) di Koltiva | Reserve |  |  | 2021-10-04
631 | MMP | Payment | Sertifikasi | Bank UOB Indonesia | Implementasi Payment ( Update Konfigurasi System ) di UOB | Reserve |  |  | 2021-10-04
632 | MMP | Payment | Sertifikasi | Bank Bumi Arta | Implementasi Payment ( XL Paket Data Channel IB ) di BBA | Reserve |  |  | 2021-10-04
633 | MMP | Payment | Sertifikasi | Bank Bumi Arta | Implementasi Payment ( XL Paket Data Channel MB ) di BBA | Reserve |  |  | 2021-10-04
634 | RAS | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( PLN NTL - Channel MB ) di Bank Kalsel | Reserve |  |  | 2021-10-08
635 | AUF | Payment | Sertifikasi | Bank Kalsel | Implementasi Payment ( PLN NTL - Channel ATM) di Bank Kalsel | Reserve |  |  | 2021-10-08
636 | WGH | Payment | Sertifikasi | PT Global Digital Niaga Blibli | Implementasi Payment ( Signal ) di BliBli | Reserve |  |  | 2021-10-13
637 | ARE | ATM Bersama QR | Sertifikasi | Bank Syariah Mandiri | Implementasi ATMB QR ( Dynamic QR as Acquirer MPM - Perpanjangan 1) di BSI | Reserve |  |  | 2021-10-13
638 | INA | ATM Bersama | Sertifikasi | Bank Syariah Mandiri | Implementasi ATM Bersama ( Layanan VA ) di BSI | Reserve |  |  | 2021-10-13
639 | AAN | ATM Bersama | Internal Test | Bank MANTAP | Internal Test ATM Bersama ( Support Kebutuhan UAT Testing CR Multijurnal untuk koneksi ATM Bersama dan Host OSSW ) di Bank Mantap | On Progress |  |  | 2021-10-13
640 | MDI | ATM Bersama QR | Sertifikasi | BJBS | Implementasi ATMB QR ( MPM as Acquirer ) di BJBS | Reserve |  |  | 2021-10-13
641 | RAS | Payment | Sertifikasi | PT Tokopedia | Implementasi Payment ( Takaful ) di Tokopedia | Reserve |  |  | 2021-10-13
642 | RAS | Payment | Sertifikasi | PT Tokopedia | Implementasi Payment ( Sunlife ) di Tokopedia | Reserve |  |  | 2021-10-13
643 | RMT | Payment | Internal Test | Bank DKI | Internal Test Payment ( Indosat Paket Data - Perubahan Paket Data ) di Bank DKI | Reserve |  |  | 2021-10-25
644 | RMT | Payment | Internal Test | Bank DKI | Internal Test Payment ( Signal ) di Bank DKI | Reserve |  |  | 2021-10-25